## Board Report (Dev) (hidden)
PROJECT Budget
CLR Silsbee PO LLC
Application Period: 12.2024
Requisition:
| Requisition Total | Approved Budget | $/RSF | Payment To Date | Balance To Pay | % Paid | Project NRSF
| LAND | 0 | 0 | 0 | 0 | 0% | 222677
| SITEWORK | 0 | 0 | 0 | 0 | 0%
| CONSTRUCTION - BASE | 6379396.92 | 28.6487 | 5467355.15 | 912041.77 | 85.7%
| PERMITS AND FEES | 0 | 0 | 0 | 0 | 0%
| DESIGN AND ENGINEERING CONSULTANTS | 164385.7 | 0.73822 | 164385.7 | 0 | 100%
| FINANCING | 2586495.53 | 11.6155 | 735654.03 | 1850841.5 | 28.44%
| OTHER DEVELOPMENT COSTS | 329018.68 | 1.4776 | 291272.4752 | 37746.2048 | 88.53%
| LEASING AND MARKETING | 1416100.7 | 6.3594 | 917186.84 | 498913.86 | 64.77%
| TOTAL PROJECT COSTS | 10875397.53 | 48.8393 | 7575854.1952 | 3299543.3348 | 69.66%
|  | 0 |  | 0 | 0

## Budget to Actual P1
[6 empty] | change date in line #9 | change date in line #9 | change date in line #9 |  | 2026-07-31
County Line Rail Silsbee LLC
Budget to Actual
2026-07-31
|  | Silsbee PO | Previous Contingency | Current Contingency | Silsbee PO | Previous Application | Payment this period | Total Complete & Draw To Date |  | Balance remaining
GL Coding | Account Name | Approved Budget | Funding & Reallocation | Funding & Reallocation | Current Approved Budget | Inception to 06/30/2026 | 7/31/2026 | Incurred to 7/31/2026 | Percent Drawn | As of 7/31/2026
| Land Purchase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11010 | Acquisitions Costs (Land Purchase) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Other Land Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Total Land Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Offsite Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Site Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Utilities Relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Total Site Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
11230-1 | Yard Stabilization | 100000 | 2678658.44 | 0 | 2778658.44 | 2778658.44 | 0 | 2778658.44 | 100% | 0
11230-2 | Warehouse Improvements | 814195 | 336094.78 | 0 | 1150289.78 | 1150289.78 | 0 | 1150289.78 | 100% | 0
11230-3 | Sprinkler Improvements | 143563 | 480944 | 0 | 624507 | 537651.9 | 86855.1 | 624507 | 100% | 0
11230-4 | Roof Improvements | 210385 | 300 | 0 | 210685 | 210685 | 0 | 210685 | 100% | 0
11230-5 | Electrical Improvements | 222358 | 79782.64 | 0 | 302140.64 | 206823.46 | 95317.18 | 302140.64 | 100% | 0
11230-6 | Fencing | 650000 | 0 | 0 | 650000 | 112500 | 0 | 112500 | 17.31% | 537500
11230-7 | Other Hard Costs | 83393 | 205181.29 | 0 | 288574.29 | 288574.29 | 0 | 288574.29 | 100% | 0
11216 | Hard Cost Contingency | 346282.8 | -221655.29 | 0 | 124627.51 | 0 | 0 | 0 | 0% | 124627.51
11217 | Soft Cost Contingency | 293570.38 | -43656.12 | 0 | 249914.26 | 0 | 0 | 0 | 0% | 249914.26
| Construction Costs | 2863747.18 | 3515649.74 | 0 | 6379396.92 | 5285182.87 | 182172.28 | 5467355.15 | 85.7% | 912041.77
| Sanitary Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Water Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Building Permits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| CO Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| A&E Permit Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| File & Review Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Tax Abatement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Zoning Variances Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - General | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - School | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Impact Fees - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Permits and Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Construction Management Fees |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12115 | A&E | 53750 | 34396.36 | 0 | 88146.36 | 88146.36 | 0 | 88146.36 | 100% | 0
12116 | Environmental (incl. Enviro Insurance) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11760 | Other Due Diligence | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12013 | Civil Engineering Plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12127 | General Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Accessibility Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Pool Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Moisture Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Renderings & Models | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Reproduction/Printing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Reimbursable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Revisions/Change Orders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Bidding, Negotiation & Admin Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Travel - Architectural and Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Permits/Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Architectural % of Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Corp Setup accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Tax Preparation accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12230 | Professional Services - Accounting | 72000 | 4239.34 | 0 | 76239.34 | 69274.24 | 6965.1 | 76239.34 | 100% | 0
| Other Accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Design and Engineering Consultants | 125750 | 38635.7 | 0 | 164385.7 | 157420.6 | 6965.1 | 164385.7 | 100% | 0
11970 | Legal | 50000 | 18086.04 | 0 | 68086.04 | 68086.04 | 0 | 68086.04 | 100% | 0
12343 | Loan Fees | 115935.11 | 29172.33 | 0 | 145107.44 | 145107.44 | 0 | 145107.44 | 100% | 0
| Capitalized Interest, Insurance, and Taxes |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12411 | Interest Rate Cap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12310 | Appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Market/Feasibility Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Predevelopment Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Investor Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Points on Equity (LP Fee) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Debt Placement Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Development Oversight Fee (LP FEE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12596 | Closing Fees | 100000 | -41697.95 | 0 | 58302.05 | 0 | 0 | 0 | 0% | 58302.05
| Bank Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Inspections/Feasibility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Architectural Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Title Updates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Letter of Credit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Applications Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12385 | Other Finance Costs (Loan Cap) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12410 | Property Tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12421 | Property Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Guarantee Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| LeaseUp Operating Deficits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12321 | Construction Period Interest | 2315000 | 0 | 0 | 2315000 | 458105.13 | 64355.42 | 522460.55 | 22.57% | 1792539.45
| Total Financing & Other Costs | 2580935.11 | 5560.42 | 0 | 2586495.53 | 671298.61 | 64355.42 | 735654.03 | 28.44% | 1850841.5
| GL Construction Insurance |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Development Management Fee |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Copies & Reproduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12720 | Travel - Other Development Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12381 | Acquisition Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Builder's Risk Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Property Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| OCIP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Telecommunications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Water/Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Warranty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Other Warranty and Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12913 | Developer Fee | 329018.68 | 0 | 0 | 329018.68 | 281132.7632 | 10139.712 | 291272.4752 | 88.53% | 37746.2048
| Development Fee - BROZ 5321 Fund LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Total Other Development Costs | 329018.68 | 0 | 0 | 329018.68 | 281132.7632 | 10139.712 | 291272.4752 | 88.53% | 37746.2048
| Closing Cost/Other |  | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12594 | Broker Commissions | 1416100.7 | 0 | 0 | 1416100.7 | 917186.84 | 0 | 917186.84 | 64.77% | 498913.86
| Closing Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Other Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Marketing Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Commercial Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Other Commercial Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| Total Leasing and Marketing | 1416100.7 | 0 | 0 | 1416100.7 | 917186.84 | 0 | 917186.84 | 64.77% | 498913.86
| Zone Project Costs - All | 7315551.67 | 3559845.86 | 0 | 10875397.53 | 7312221.6832 | 263632.512 | 7575854.1952 | 69.66% | 3299543.3348
[5 empty] | Total Project Costs incurred per GL |  |  | 3923740.1
[5 empty] | Total Project Costs incurred per Master Report |  |  | 7575854.1952
[5 empty] | Discrepancy (Scrap cost recovered) |  |  | -3652114.0952
[5 empty] | Proceeds from Proler |  |  | 0
[5 empty] | Gain/(Loss) on Scrap Sales |  |  | -3652114.0952
Project Costs recorded in Master Report but not in the GL
0
0
Cross Check |  | TRUE | TRUE | TRUE |  | TRUE | TRUE | 3923740.1 | Total Project Costs per Budget to Actual
|  | Zone Project Cost - All = Board Report | PC Total should be zero | CC total should be zero |  | BTA = Prior Inv Log | BTA = Current Inv Log | 14444739.25 | Total Project Costs per Exp Analysis
FALSE
[7 empty] | #REF! | #REF!
BTA = Dev Fee

## Soft Cost Contingency P1
County Line Rail Silsbee LLC
Soft Cost Contingency Table
2026-06-30
| Cost Category | Contingency | Contingency | Contingency | Req # | Notes
|  | Previously | Requested | Total
COA# |  | Requested | Herein | Requested
11230-5 | Electrical Improvements | -540 |  |  | 10 | Budget adjustment
12230 | Professional Services - Accounting | 4239.34 |  |  | 10 | Budget overrun on accounting
12115 | A&E | 2868.08 |  |  | 9 | Budget overrun on A&E
12115 | A&E | 5802.86 |  |  | 8 | Budget overrun on A&E
11970 | Legal | 5560.42 |  |  | 7 | Budget overrun on Legal
12115 | A&E | 5000 |  |  | 7 | Budget overrun on A&E
12115 | A&E | 9943.8 |  |  | 6 | Budget overrun on A&E
12115 | A&E | 10781.62 |  |  | 5 | Budget overrun on A&E
| Total Other Development Costs | 39956.78 | 3699.34 | 43656.12
Contingency Allocations |  | 39956.78 | 3699.34 | 43656.12
Original Contingency Budget |  | 293570.38
Contingency Previously Requested |  | 39956.78
Contingency Requested Herein |  | 3699.34
Total Contingency Requested |  | 43656.12
Remaining Contingency |  | 249914.26
|  | TRUE | Budget to Actual = Soft Cost Contingency Table

## Soft cost contingency-PSTR (hidden)
| Cost Category | Contingency | Contingency | Contingency | Req | Notes
|  | Previously | Requested | Total
COA# |  | Requested | Herein | Requested
| Land | 0.36 |  |  | 1
| Due Diligence | 1949.64 |  |  | 1
| Total Other Development Costs | 1950 | 0 | 1950
Contingency Allocations |  | 1950 | 0 | 1950
Original Contingency Budget |  | #REF!
Contingency Previously Requested |  | 1950
Contingency Requested Herein |  | 0
Total Contingency Requested |  | 1950
Remaining Contingency |  | #REF!
#REF!

## Hard cost contingency (hidden)
| Cost Category | Contingency | Contingency | Req | Notes
|  | Previously | Requested
COA# |  | Requested | Herein
Reference Hidden Tab "Bridge Approvd Budget to Actual"
Added 489,803.90 to Orginal Budget (1,914,611.10)
0
| Total Other Development Costs | 0 | 0
Contingency Allocations |  | 0 | 0
Original Contingency Budget |  | #REF!
Contingency Previously Requested |  | 0
Contingency Requested Herein |  | 0
Total Contingency Requested |  | 0
Remaining Contingency |  | #REF!
#REF!

## Hard Cost Contigency P1
County Line Rail Silsbee LLC
Hard Cost Contingency Table
2026-06-30
| Cost Category | Contingency | Contingency | Contingency | Req # | Notes
|  | Previously | Requested | Total
COA# |  | Requested | Herein | Requested
0
11230-3 | Sprinkler Improvements | 16174 |  |  | 10 | Budget Reallocation
11230-7 | Other Hard Costs | 15561.43 |  |  | 8 | Budget Reallocation
11230-1 | Yard Stabilization | 48645.39 |  |  | 7 | Budget Reallocation
11230-4 | Roof Improvements | 300 |  |  | 6 | Budget Reallocation
11230-7 | Other Hard Costs | 12605.92 |  |  | 6 | Budget Reallocation
11230-7 | Other Hard Costs | 19200.94 |  |  | 5 | Budget Reallocation
11230-7 | Other Hard Costs | 109167.61 |  |  | 4 | Budget Reallocation
| Total Other Development Costs | 205481.29 | 16174 | 221655.29
Contingency Allocations |  | 205481.29 | 16174 | 221655.29
Original Contingency Budget |  | 346282.8
Contingency Previously Requested |  | 205481.29
Contingency Requested Herein |  | 16174
Total Contingency Requested |  | 221655.29
Remaining Contingency |  | 124627.51
|  | TRUE | Budget to Actual = Hard Cost Contingency Table

## Current Invoice Log P1
County Line Rail Silsbee LLC
Current Invoice Log
2026-06-30
Cost Category | Bank Cost Category | Cost Code # | Cost Code Name | Vendor | Bill number | Amount | Requisition Month | Invoice (Y/N)
Professional Services - Accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261457720 | 6912.36 | Req#11 |  | 2026-07-27 | 12230
Professional Services - Accounting Total
Construction Period Interest |  | 12321 | Construction Period Interest | BoTX | Jul_26 Interest | 62794.4 | Req#11 |  | 2026-07-13 | 12321
Construction Period Interest Total
Soft Costs | Development Fee | 12913 | Development Fee | County Line Rail Interest | July_26 Dev Fee | 10049.82 | Req#11 |  |  | 12913
Development Fee Total
Broker Commissions |  | 12594 | Broker Commissions | DFW Lee & Associates, LLC - Houston Office, RS | 20256631-1 | 181538.72 | Req#11 |  | 2026-07-01 | 12594
Broker Commissions Total
Grand Total

## Prior Invoice Log P1
County Line Rail Silsbee LLC
Prior Invoice Log
2026-06-30
Cost Category | Bank Cost Category | Cost Code # | Cost Code Name | Vendor | Bill number | Amount Paid | Requisition Month | Invoice
Land Cost |  | 11010 | Acquisitions Costs (Land Purchase)
Acquisitions Costs (Land Purchase) Total
Construction Costs |  | 11210 | Expansion Costs (Base Construction Costs)
Construction Costs |  | 11210 | Expansion Costs (Base Construction Costs)
Expansion Costs (Base Construction Costs) Total
Construction Cost |  | 11212 | Other Structures (BNSF 418 Road Crossing Install)
Construction Cost |  | 11212 | Other Structures (BNSF 418 Road Crossing Install)
Construction Cost |  | 11212 | Other Structures (BNSF 418 Road Crossing Install)
Other Structures (BNSF 418 Road Crossing Install) Total
Construction Cost |  | 11213 | Track Clearing Repair
Construction Cost |  | 11213 | Track Clearing Repair
Construction Cost |  | 11213 | Track Clearing Repair
Track Clearing Repair Total
Construction Costs |  | 11214 | Building Repair (waterproofing)
Construction Costs |  | 11214 | Building Repair (waterproofing)
Construction Cost |  | 11214 | Building Repair |  |  | 0
Building Repair (waterproofing) Total
Construction Cost |  | 11215 | Deferred Maintenance
Construction Cost |  | 11215 | Deferred Maintenance
Construction Cost |  | 11215 | Deferred Maintenance
Base Construction Costs Total
Construction Cost |  | 11218 | Working Capital
Construction Cost |  | 11218 | Working Capital
Working Capital Total
Design and Engineering Consultants |  | 12115 | A&E
Design and Engineering Consultants |  | 12115 | A&E
Design and Engineering Consultants |  | 12115 | A&E | TRC | 50631
Appraisal |  | 12115 | Appraisal | Colliers International
Appraisal |  | 12115 | Appraisal | Colliers International
A&E Total
Design and Engineering Consultants |  | 12116 | Environmental
Design and Engineering Consultants |  | 12116 | Environmental
Design and Engineering Consultants |  | 12116 | Environmental
Environmental Total
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App#1 | 142534.8 | Rec #1
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App#1 | 110286.65 | Rec #1
Other Construction Costs |  | 11230-7 | Other Construction Costs | Water Asset Holdings | CLR2509 | 5000 | Rec #1
Other Construction Costs |  | 11230-7 | Other Construction Costs | Double S Industrial Contractors, Inc. | 125-2901-A | 17733 | Rec #1
Other Construction Costs |  | 11230-7 | Other Construction Costs | Ram Industrial Construction | 17431 | 5000 | Rec #1 |  |  | In January GL, Not on Req Report
Other Construction Costs |  | 11230-7 | Other Construction Costs | Switch Yard Mowing | 10001 | 15660 | Rec #1
Other Construction Costs |  | 11230-3 | Other Construction Costs | Summit Fire & Security, LLC | Pay App #1 | 129528.9 | Rec #2
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App #2 | 302767.57 | Rec #2
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App #2 | 468959.59 | Rec #2
Other Construction Costs |  | 11230-4 | Other Construction Costs | Strategic Roofing Solutions | Pay App #1 - Roofing | 35997.3 | Rec #2
Other Construction Costs |  | 11230-5 | Other Construction Costs | Biskamp Electric | Pay App #1 | 168962.15 | Rec #2
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App #3 | 267556.23 | Rec #3
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App #3R | 94089.16 | Rec #3
Other Construction Costs |  | 11230-4 | Other Construction Costs | Strategic Roofing Solutions | Pay App #2 | 51808.5 | Rec #3
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App #3 | 867999.29 | Rec #3
Other Construction Costs |  | 11230-7 | Other Construction Costs | Bartlett & West | 730105520 | 25750 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Bartlett & West | 730106293 | 21750 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Bartlett & West | 730106835 | 4500 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 788993 | 5298.84 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Bartlett & West | 730107424 | 6750 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Curtis Oilfield Services | 60176 | 25257.43 | Rec #4
Other Construction Costs |  | 11230-3 | Other Construction Costs | Summit Fire & Security | Pay App #2 | 330021 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 789010 | 4995 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 789013 | 52666.34 | Rec #4
Other Construction Costs |  | 11230-7 | Other Construction Costs | Tony's Concrete | 122225 | 2200 | Rec #4
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App #4 | 205206.34 | Rec #4
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App #4 | 651523.95 | Rec #5
Other Construction Costs |  | 11230-2 | Other Construction Costs | Stewart Development & Construction, LLC | Pay App #4R | 4191.81 | Rec #5
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 789022 | 5168.94 | Rec #5
Other Construction Costs |  | 11230-7 | Other Construction Costs | Bartlett & West | 730107842 | 14032 | Rec #5
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App #5 | 500751.11 | Rec #6
Other Construction Costs |  | 11230-7 | Other Construction Costs | XC Container LLC | SO09612 | 12605.92 | Rec #6
Other Construction Costs |  | 11230-4 | Other Construction Costs | Strategic Roofing Solutions | Pay App #3 | 80768.7 | Rec #6
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App#6R | 277865.84 | Rec #7
Other Construction Costs |  | 11230-6 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App#1b | 148500 | Rec #7
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 789096 | 45863.36 | Rec #7
Other Construction Costs |  | 11230-1 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App#6 | 35215.88 | Rec #7
Other Construction Costs |  | 11230-7 | Other Construction Costs | Agri-Serv Industrial Maintenance | 789081 | 2782.03 | Rec #7
Other Construction Costs |  | 11230-4 | Other Construction Costs | Strategic Roofing Solutions | Pay App#4 | 21042 | Rec #7
Other Construction Costs |  | 11230-4 | Other Construction Costs | Strategic Roofing Solutions | Pay App#5R | 21068.5 | Rec #7
Other Construction Costs |  | 11230-7 | Other Construction Costs | Choctaw Construction Services | 26-2754-1 | 7505.4 | Rec #8
Other Construction Costs |  | 11230-7 | Other Construction Costs | Choctaw Construction Services | 26-2759-1 | 8056.03 | Rec #8
Other Construction Costs |  | 11230-5 | Other Construction Costs | Biskamp Electric | Pay App #2 | 37861.31 | Rec #8
Other Construction Costs |  | 11230-3 | Other Construction Costs | Summit Fire & Security | Pay App #3 | 78102 | Rec #8
Other Construction Costs |  | 11230-6 | Other Construction Costs | Agri-Serv Industrial Maintenance | Pay App#1b (revised) | -36000 | Rec #8
Expansion Costs (Base Construction Costs) Total
Design and Engineering Consultants |  | 11760 | Other Due Diligence
Design and Engineering Consultants |  | 11760 | Other Due Diligence
Design and Engineering Consultants |  | 11760 | Other Due Diligence
Other Due Diligence Total
Financing & Other Costs |  | 11970 | Other Legal - Legal | Mira Blanton PLLC | 20250109 | 5000 | Rec #1 |  |  | In January GL, Not on Req Report
Financing & Other Costs |  | 11970 | Other Legal - Legal | Jack Holmes | 303 | 2561 | Rec #1 |  |  | In April GL, Not on Req Report
Financing & Other Costs |  | 11970 | Other Legal - Legal | Jack Holmes | 304 | 1928 | Rec #1 |  |  | In May GL, Not on Req Report
Financing & Other Costs |  | 11970 | Other Legal - Legal | Jack Holmes | 308 | 1568 | Rec #1 |  |  | In August GL, Not on Req Report
Financing & Other Costs |  | 11970 | Other Legal - Legal | Patrick M Knapp | 022 | 2379 | Rec #1
Financing & Other Costs |  | 11970 | Other Legal - Legal | Troutman Pepper Locke | 132053245 | 1207 | Rec #1
Financing & Other Costs |  | 11970 | Other Legal - Legal | Jack Holmes | 309 | 794 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | Mira Blanton PLLC | 3509 | 5505 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | Mira Blanton PLLC | 3510 | 832.89 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | Mira Blanton PLLC | 3511 | 2381.32 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | Mira Blanton PLLC | 3249 | 1115 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | CLRFI | ADJ JE CLR Fund Loan Closing | 18812.66 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | BoTX | BoTX Loan Closing ADJ JE | 18441.75 | Rec #4
Financing & Other Costs |  | 11970 | Other Legal - Legal | L.E. Peabody | Feb_2026 | 5560.42 | Rec #7
Financing & Other Costs |  | 11970 | Other Legal - Legal | L.E. Peabody
Other Legal - Legal Total
Construction Costs |  | 12013 | Civil Engineering Plans
Construction Costs |  | 12013 | Civil Engineering Plans
Civil Engineering Plans Total
Design and Engineering Consultants |  | 12115 | A&E | TRC | 48204 | 3836.1 | Rec #1
Appraisal |  | 12115 | Appraisal | Colliers International | 536237 | 6500 | Rec #1
Appraisal |  | 12115 | Appraisal | Colliers International | 536249 (Silsbee Portion) | 625 | Rec #1
Design and Engineering Consultants |  | 12115 | A&E | TRC | 48561 | 4233.98 | Rec #2
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2510 | 5000 | Rec #2
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR251003 | 1500 | Rec #2
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2511 | 5000 | Rec #3
Design and Engineering Consultants |  | 12115 | A&E | TRC | 49013 | 719 | Rec #3
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2512 | 5000 | Rec #4
Design and Engineering Consultants |  | 12115 | A&E | TRC | 49136 | 19901.12 | Rec #4
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2601 | 5000 | Rec #5
Design and Engineering Consultants |  | 12115 | A&E | TRC | 49488 | 1816.42 | Rec #5
Design and Engineering Consultants |  | 12115 | A&E | Access Surveyors | 20251052-1 | 4600 | Rec #5
Other Construction Costs |  | 12115 | A&E | Southeast Texas Groundwater Cons. | 01.28.25WellPermits | 400 | Rec #5
Other Construction Costs |  | 12115 | A&E | Southeast Texas Groundwater Cons. | 01.28.25WellPermits | 400 | Rec #5
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2602 | 5000 | Rec #6
Design and Engineering Consultants |  | 12115 | A&E | Access Surveyors | 2026056-1 | 2200 | Rec #6
Design and Engineering Consultants |  | 12115 | A&E | Access Surveyors | 2026088-1 | 2600 | Rec #6
Other Construction Costs |  | 12115 | A&E | TRC | 49841 | 143.8 | Rec #6
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2603 | 5000 | Rec #7
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR2604 | 5000 | Rec #8
Design and Engineering Consultants |  | 12115 | A&E | Water Asset Holdings | CLR260415 | 802.86 | Rec #8
Design and Engineering Consultants |  | 12115 | A&E | TRC | 50631 | 2868.08 | Rec #9
A&E Total
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L251572229 | 5484.61 | Rec #1
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L251635995 | 8817.86 | Rec #2
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L251712193 | 8014.17 | Rec #3
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261008873 | 5587 | Rec #4 |  | - Accrual for December portion of CLA inv
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261008873 | 8834.97 | Rec #5
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261093961 | 9216.43 | Rec #6
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261125750 | 11420.68 | Rec #7
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | Reclassed fees from Dec_25 | -200.35 | Rec #7
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261196046 | 3296.63 | Rec #8
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261295566 | 8802.24 | Rec #9
Professional Services accounting |  | 12230 | Professional Services - Accounting | CliftonLarsonAllen LLP | L261385889 | 6965.1 | Rec #10
Professional Services - Accounting Total
Financing & Other Costs |  | 12321 | Construction Period Interest | Sunflower Bank | CLR Fund Loan Closing | 17850.66 | Rec #1
Financing & Other Costs |  | 12321 | Construction Period Interest | Sunflower Bank | CLR Fund Loan Closing | 4953.4 | Rec #1
Financing & Other Costs |  | 12321 | Construction Period Interest | Sunflower Bank | CLR Fund Loan Closing | 25142.37 | Rec #1
Financing & Other Costs |  | 12321 | Construction Period Interest | Sunflower Bank | Oct_25 Capitalized Interest (CLRFI) | 27003.51 | Rec #2
Financing & Other Costs |  | 12321 | Construction Period Interest | Sunflower Bank | ADJ JE CLR Fund Loan Closing | 43463.32 | Rec #4
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | BoTX Loan Closing ADJ JE | 133594.08 | Rec #4
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Jan_26 Interest Accrual 1-14 | 19839.05 | Rec #5
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Jan_26 Interest Accrual 1-14 | 2769.86 | Rec #5
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Feb_26 Interest 2-15 | 47767.91 | Rec #6
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Mar_26 Interest 3/15 | 49199.04 | Rec #7
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Apr_26 Interest 4/15 | 26183.61 | Rec #8
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | May_26 Interest Accrual 16-31 | 60338.32 | Rec #9
Financing & Other Costs |  | 12321 | Construction Period Interest | BoTX | Jun_26 Interest Accrual 16-31 | 64355.42 | Rec #10
Construction Period Interest Total
Loan Fees |  | 12343 | Loan Fees | Sunflower Bank | CLR Fund Loan Closing | 345.35 | Rec #1
Loan Fees |  | 12343 | Loan Fees | Sunflower Bank | CLR Fund Loan Closing | 919.68 | Rec #1
Loan Fees |  | 12343 | Loan Fees | Sunflower Bank | CLR Fund Loan Closing | 2299.19 | Rec #1
Loan Fees |  | 12343 | Loan Fees | Sunflower Bank | ADJ JE CLR Fund Loan Closing | 25608.09 | Rec #4
Loan Fees |  | 12343 | Loan Fees | BoTX | BoTX Loan Closing ADJ JE | 115935.13 | Rec #4
Loan Fees |  | 12343 | Loan Fees | Sunflower Bank
Loan Fees |  | 12343 | Loan Fees | BoTX
Loan Fees Total
Financing & Other Costs |  | 12310 | Appraisal
Financing & Other Costs |  | 12310 | Appraisal
Appraisal Total
Other Development Costs |  | 12381 | Acquisition Fees
Acquisition Fees Total
Financing & Other Costs |  | 12385 | Other Finance Costs (Loan Cap)
Financing & Other Costs |  | 12385 | Other Finance Costs (Loan Cap)
Other Finance Costs (Loan Cap) Total
Financing & Other Costs |  | 12410 | Capitalized Property Tax
Financing & Other Costs |  | 12410 | Capitalized Property Tax
Financing & Other Costs |  | 12410 | Capitalized Property Tax
Capitalized Property Tax Total
Financing & Other Costs |  | 12421 | Property Insurance
Financing & Other Costs |  | 12421 | Property Insurance
Financing & Other Costs |  | 12421 | Property Insurance
Property Insurance Total
Broker Commissions |  | 12594 | Broker Commissions | M&W Real Estate | 18 | 135836.41 | Rec #1
Broker Commissions |  | 12594 | Broker Commissions | DFW Lee & Associates | 09042025 | 781350.43 | Rec #1
Broker Commissions |  | 12594 | Broker Commissions | M&W Real Estate
Broker Commissions |  | 12594 | Broker Commissions | DFW Lee & Associates
|  |  | Broker Commissions Total | [7 empty] | 15059922.7 | FALSE
Other Development Costs |  | 12720 | Travel - Other Development Costs
Other Development Costs |  | 12720 | Travel - Other Development Costs
Travel - Other Development Costs Total
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Sep_25 Dev Fee | 51840.03 | Rec #1
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Oct_25 Dev Fee | 46110.83 | Rec #2
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Nov_25 Dev Fee | 51807.45 | Rec #3
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Dec_25 Dev Fee | 43254.6524 | Rec #4
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Jan_25 Dev Fee | 28632.29 | Rec #5
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Feb_25 Dev Fee | 26442.1548 | Rec #6
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Mar_25 Dev Fee | 24932.696 | Rec #7
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Apr_25 Dev Fee | 5232.31 | Rec #8
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | May_25 Dev Fee | 2880.35 | Rec #9
Other Development Costs |  | 12913 | Developer Fee | Banyan Residential | Jun_26 Dev Fee | 10139.712 | Rec #10
Developer Fee Total
Other Construction Costs |  | 11230-3 | Office Buildout | Summit Fire & Security | Pay App #4 | 24404.4 | Rec #10
Other Construction Costs |  | 11230-3 | Office Buildout | Summit Fire & Security | Pay App #4R | 62450.7 | Rec #10
Office Buildout Total
Other Construction Costs |  | 11230-5 | Office Buildout | Biskamp Electric | Pay App #3 | 65103.12 | Rec #10
Other Construction Costs |  | 11230-5 | Office Buildout | Biskamp Electric | Pay App #3R | 30214.06 | Rec #10
Office Buildout Total
Grant Total

## Dev Fee P1
County Line Rail Silsbee
Development Fee Calculation
2026-06-30
| Project costs | Project costs | Project costs
| Incurred to date | Incurred - Month of | Incurred
| 2026-06-30 | 2026-06-30 | 2026-05-31
Project costs
Hard Costs | 5467355.15 | 182172.28 | 5285182.87
Soft Costs | 1817226.57 | 71320.52 | 1745906.05
0
Total | 7284581.72 | 253492.8 | 7031088.92
Total per GL
Discrepancy | 7284581.72
Development fees: | Dev fees incurred to date | Current Month Dev Fee | Prior Month Balance
Due to CLR Silsbee Property Owner | 291383.27 | 10139.712 | 281243.56
Total: | 291383.27 | 0 | 281243.56
| Total | 10139.712
Formulas:
Project costs = [Project costs]

## Budget to Actual (OP) (hidden)
PROJECT FUNDING REQUISITION
County Line Rail Silsbee LLC
Application Period: 12/31/2025
Requisition Report #17
| Operations | Silsbee PO | Previous Contingency | Current Contingency | Silsbee PO | Previous Application | Payment this period | Total Complete & Draw To Date |  | Balance remaining
GL Coding | Account Name | Approved Budget | Funding & Reallocation | Funding & Reallocation | Current Approved Budget | Inception to 11/30/2025 | 2025-12-31 | Incurred to 12/31/2025 | Percent Drawn | As of 12/31/2025
40120 | In & Out Fees | 303525 | 0 | 0 | 303525 | 66483 | 0 | 66483 | 21.9% | 237042
40130 | Storage Fees | 681507.2 | 0 | 0 | 681507.2 | 588015 | 0 | 588015 | 86.28% | 93492.2
40140 | Transloading Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
40160 | Intra Plant Switch Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
40400 | Concessions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
40451 | Bad Debt | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total Rail Income | 985032.2 | 0 | 0 | 985032.2 | 654498 | 0 | 654498 | 108% | 330534.2
40110 | Short Term Land Leases | 138000 | 0 | 0 | 138000 | 130360 | 0 | 130360 | 94.46% | 7640
40140 | Intra-Plant Switch Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
40150 | Warehouse Lease Income | 700000 | 0 | 0 | 700000 | 200000 | 0 | 200000 | 28.57% | 500000
40160 | Transloading Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
41114 | Late Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total Other Income | 838000 | 0 | 0 | 838000 | 330360 | 0 | 330360 | 39.42% | 507640
| Total Income | 1823032.2 | 0 | 0 | 1823032.2 | 984858 | 0 | 984858 | 54.02% | 838174.2
63034 | Switchmen Salaries - Reimbursable | 147792.69 | 0 | 0 | 147792.69 | 163556.67 | 11560.34 | 175117.01 | 118.5% | -27324.32
63032 | Switchmen Healthcare – Reimbursable | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
63033 | Mowing Assistance - Reimbursable | 36000 | 0 | 0 | 36000 | 17150 | 0 | 17150 | 47.64% | 18850
63041 | Onsite Manager | 101165.26 | 0 | 0 | 101165.26 | 0 | 0 | 0 | 0% | 101165.26
63042 | Overtime | 18000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0% | 18000
64000 | Security | 80004 | 0 | 0 | 80004 | 82034.61 | 6245.3 | 88279.91 | 110.3% | -8275.91
63028 | Asset Manager - (County Line) | 22500 | 0 | 0 | 22500 | 13125 | 0 | 13125 | 58.33% | 9375
63036 | Accounting (County Line) | 22500 | 0 | 0 | 22500 | 13125 | 0 | 13125 | 58.33% | 9375
63040 | Business Development (County Line) | 60000 | 0 | 0 | 60000 | 35000 | 0 | 35000 | 58.33% | 25000
63041 | Offsite Manager | 0 | 0 | 0 | 0 | 18592.12 | -1603.53 | 16988.59 | 0% | -16988.59
63042 | Offsite Staff | 0 | 0 | 0 | 0 | 51130.03 | 10116.6 | 61246.63 | 0% | -61246.63 | <-- Non-Budgeted Item
| Total Payroll | 487961.95 | 0 | 0 | 487961.95 | 393713.43 | 26318.71 | 420032.14 | 86.08% | 67929.81
63025 | Professional Fees | 0 | 0 | 0 | 0 | 7141.37 | 1.25 | 7142.62 | 0% | -7142.62 | <-- Non-Budgeted Item
63050 | Legal Fees | 18000 | 0 | 0 | 18000 | 66630.31 | 0 | 66630.31 | 370.2% | -48630.31
63100 | Consulting Fees | 10000 | 0 | 0 | 10000 | 17876.26 | 0 | 17876.26 | 178.8% | -7876.26
67100 | Dues & Subscriptions | 0 | 0 | 0 | 0 | 1560 | 0 | 1560 | 0% | -1560
67200 | Office Expense | 12000 | 0 | 0 | 12000 | 3099.65 | 366.67 | 3466.32 | 28.89% | 8533.68
67250 | Postage and Delivery | 600 | 0 | 0 | 600 | 0 | 0 | 0 | 0% | 600
67300 | Telephone & Internet | 1200 | 0 | 0 | 1200 | 0 | 0 | 0 | 0% | 1200
67400 | Advertising & Marketing | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0% | 12000
68110 | Bank Fees | 500 | 0 | 0 | 500 | 910 | 0 | 910 | 182% | -410
| Inventory Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
63000 | Accounting Fees | 65688 | 0 | 0 | 65688 | 52091.38 | 0 | 52091.38 | 79.3% | 13596.62
60210 | Travel | 0 | 0 | 0 | 0 | 7744.65 | 217.32 | 7961.97 | 0% | -7961.97 | <-- Non-Budgeted Item
60500 | Meals | 0 | 0 | 0 | 0 | 546.54 | 158.16 | 704.7 | 0% | -704.7 | <-- Non-Budgeted Item
| Total Admin | 119988 | 0 | 0 | 119988 | 150458.79 | 742.15 | 151200.94 | 126% | -31212.94
61051 | Track Repairs | 20000 | 0 | 0 | 20000 | 1775 | 0 | 1775 | 8.875% | 18225
| Switch Repairs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
61052 | Crossing Repairs | 20004 | 0 | 0 | 20004 | 9164 | 700 | 9864 | 49.31% | 10140
61054 | Locomotive Repair | 18000 | 0 | 0 | 18000 | 0 | 0 | 0 | 0% | 18000
61056 | Landscape Maintenance | 0 | 0 | 0 | 0 | 12500 | 2500 | 15000 | 0% | -15000 | <-- Non-Budgeted Item
61050 | Site/Yard Maintenace | 30000 | 0 | 0 | 30000 | 7444.67 | 1061.6 | 8506.27 | 28.35% | 21493.73
| Road Repairs | 3000 | 0 | 0 | 3000 | 0 | 0 | 0 | 0% | 3000
| Vehicle Repairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Other Repairs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| Total Maintenance | 91004 | 0 | 0 | 91004 | 30883.67 | 4261.6 | 35145.27 | 38.62% | 55858.73
61164 | Fuel | 30000 | 0 | 0 | 30000 | 8554.35 | 3969.31 | 12523.66 | 41.75% | 17476.34
| Locomotive Lease | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
68105 | Demurrage Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| (Other) | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0
| Total Service/Operating Expenses | 30000 | 0 | 0 | 30000 | 8554.35 | 3969.31 | 12523.66 | 41.75% | 17476.34
63026 | Management Fees - Hall Logistics | 123643.22 | 0 | 0 | 123643.22 | 45640.01 | 0 | 45640.01 | 36.91% | 78003.21
63038 | Management Fees - County Line | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
63027 | AM Fees - Banyan | 150000 | 0 | 0 | 150000 | 115915.95 | 5683.19 | 121599.14 | 81.07% | 28400.86
| Total AM/Mgmt. Fees | 273643.22 | 0 | 0 | 273643.22 | 161555.96 | 5683.19 | 167239.15 | 61.12% | 106404.07
| Total Variable Expenses | 1002597.17 | 0 | 0 | 1002597.17 | 752307.57 | 40976.21 | 793283.78 | 79.12% | 209313.39
68060 | State and Local Taxes | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
68050 | Property Tax | 115315.76 | 0 | 0 | 115315.76 | 97743.52 | -7962.63 | 89780.89 | 77.86% | 25534.87
| Builder's Risk Insurance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
68055 | Property Insurance | 191276.8 | 0 | 0 | 191276.8 | 229659.38 | 27093.47 | 256752.85 | 134.2% | -65476.05
65000 | Insurance - Liability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
61150 | Utilities | 26100 | 0 | 0 | 26100 | 36198.22 | 1184.69 | 37382.91 | 143.2% | -11282.91
| Total Fixed Expenses | 332692.56 | 0 | 0 | 332692.56 | 363601.12 | 20315.53 | 383916.65 | 115.4% | -51224.09
| Total Expenses | 1335289.73 | 0 | 0 | 1335289.73 | 1115908.69 | 61291.74 | 1177200.43 | 88.16% | 158089.3
| Net Operating Income | 487742.47 | 0 | 0 | 487742.47 | -131050.69 | -61291.74 | -192342.43 | -39.44% | 680084.9
| Projected Debt Service | 326924.83 | 0 | 0 | 326924.83 | 0 | 0 | 984858 | 301.2% | 326924.83
| Cash Flow After Debt Service | 160817.64 | 0 | 0 | 160817.64 | -131050.69 | -61291.74 | -1177200.43 | -341% | 353160.07
75000 | Interest Expense | 0 | 0 | 0 | 0 | 160698.08 | 0 | 160698.08 | 0% | -160698.08 | <-- Non-Budgeted Item
75140 | Legal Expenditures | 43000 | 0 | 0 | 43000 | 3883.45 | 0 | 3883.45 | 9.031% | 39116.55
75110 | Consultant Expenditures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
75005 | Unused Fee Expense | 0 | 0 | 0 | 0 | 3953.57 | 3285.89 | 7239.46 | 0% | -7239.46 | <-- Non-Budgeted Item
75006 | Loan Fee Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | <-- Non-Budgeted Item
| Grant Expenditures | 120000 | 0 | 0 | 120000 | 0 | 0 | 0 | 0% | 120000
| Car Reader | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0% | 30000
| Tenant Improvements | 200000 | 0 | 0 | 200000 | 0 | 0 | 0 | 0% | 200000
0
| Total Capital Expenditures | 393000 | 0 | 0 | 393000 | 168535.1 | 3285.89 | 171820.99 | 43.72% | 221179.01
| Lender portion (75%) | [5 empty] | 48433.2225
| Draw Request Total | [5 empty] | 50000
(Rounded to the nearest 10,000)
[5 empty] | Rev: | 0 | 0
[5 empty] | Expense: | 0 | 0

## Current Revenue Log (OP) (hidden)
Cost Category | Cost Code # | Cost Code Name | Customer | Invoice # | Amount Paid | Requisition Month | Invoice Date | CURRENT REQ REPORT | DUPLICATE(S)
Short Term Land Leases | 40110 | Land Leases
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1415
|  | Land Leases Total |  |  | 0
In & Out Fees | 40120 | In & Out Fees
In & Out Fees | 40120 | In & Out Fees
|  | In & Out Fees Total |  |  | 0
Storage Fees | 40130 | Storage Fees
Storage Fees | 40130 | Storage Fees
|  | Storage Fees Total |  |  | 0
Trasnloading Fees | 40140 | Transloading | Trecora Resources
|  | Transloading Total |  |  | 0
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation
|  | Warehouse Lease Total |  |  | 0
|  | Grand Total |  |  | 0

## Prior Revenue Log (OP) (hidden)
Cost Category | Cost Code # | Cost Code Name | Customer | Invoice # | Amount Paid | Requisition Month | Invoice Date | CURRENT REQ REPORT | DUPLICATE(S)
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1303 | 6500 | 2025-01-01 | 2025-02-01
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1405 | 4500 | 2025-01-01 | 2025-02-01
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1404 | 6760 | 2025-02-01 | 2025-03-04 |  |  | GL | GL Term | Invoice Term
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1406 | 4500 | 2025-02-01 | 2025-03-04 |  |  | 40110 | Short Term Land Leases | Rent - Short Term
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1405 | 6760 | 2025-03-01 | 2025-04-01 |  |  | 40120 | In & Out Fees | Inbound/Outbound Fees
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1407 | 4500 | 2025-03-01 | 2025-04-01 |  |  | 40130 | Storage Fees | Warehouse Storage, Base Spots, Overages
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1506 | 6760 | 2025-04-01 | 2025-05-01 |  |  | 40140 | Intra-Plant Switch Fees | Intra-Plant Switch Fees
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1408 | 4500 | 2025-04-01 | 2025-05-01 |  |  | 40150 | Warehouse Lease Income | Rent - Long term - Louisiana-Pacific
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1507 | 6760 | 2025-05-25 | 2025-06-01 |  |  | 40160 | Transloading Fees | Transloading Fees
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1409 | 4500 | 2025-05-25 | 2025-06-01
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1508 | 6760 | 2025-06-25 | 2025-07-02
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1411 | 4500 | 2025-06-25 | 2025-07-02
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1509 | 6760 | 2025-07-25 | 2025-07-31
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1411 | 4500 | 2025-07-25 | 2025-07-31
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1510 | 6760 | 2025-08-25 | 2025-08-31
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1412 | 4500 | 2025-08-25 | 2025-08-31
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1511 | 6760 | 2025-09-01 | 2025-09-30
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1413 | 4500 | 2025-09-01 | 2025-09-30
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1512 | 6760 | 2025-10-01 | 2025-10-31
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1414 | 4500 | 2025-10-01 | 2025-10-31
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1513 | 6760 | 2025-11-25 | 2025-11-30
Short Term Land Leases | 40110 | Land Leases | Utility Lines Construction Services | 1415 | 4500 | 2025-11-25 | 2025-11-30
Short Term Land Leases | 40110 | Land Leases | Silsbee Ford | 1514 | 6760 | 2025-12-01 | 2025-12-01
|  | Land Leases Total |  |  | 130360
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 1304 | 440 | 2025-01-01 | 2025-02-11
In & Out Fees | 40120 | In & Out Fees | Valero | 1 | 16425 | 2025-04-01 | 2025-05-02
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 8009 | 1265 | 2025-04-01 | 2025-05-02
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 8010 | 1760 | 2025-05-25 | 2025-06-01
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 8011 | 1155.5 | 2025-06-25 | 2025-07-02
In & Out Fees | 40120 | In & Out Fees | Valero | 4 | 1125 | 2025-07-25 | 2025-07-31
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 8012 | 660 | 2025-07-25 | 2025-07-31
In & Out Fees | 40120 | In & Out Fees | Valero | 5 | 15187.5 | 2025-08-25 | 2025-08-31
In & Out Fees | 40120 | In & Out Fees | Trecora Recources | 8013 | 880 | 2025-08-25 | 2025-08-31
In & Out Fees | 40120 | In & Out Fees | Valero | 6 | 13612.5 | 2025-09-01 | 2025-09-30
In & Out Fees | 40120 | In & Out Fees | Valero | 8 | 5737.5 | 2025-11-25 | 2025-11-30
In & Out Fees | 40120 | In & Out Fees | Trecora Resources | 8015 | 275 | 2025-11-25 | 2025-11-30
In & Out Fees | 40120 | In & Out Fees | Valero | 9 | 6750 | 2025-12-01 | 2025-12-31
In & Out Fees | 40120 | In & Out Fees | Trecora Resources | 8016 | 1210 | 2025-12-01 | 2025-12-31
|  | In & Out Fees Total |  |  | 66483
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1302 | 4459 | 2025-01-01 | 2025-02-11
Storage Fees | 40130 | Storage Fees | Trecora Resources | 1304 | 16740 | 2025-01-01 | 2025-02-11
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1402 | 3530 | 2025-02-01 | 2025-03-04
Storage Fees | 40130 | Storage Fees | Trecora Resources | 1304 | 15120 | 2025-02-01 | 2025-03-10
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1404 | 3530 | 2025-03-01 | 2025-04-01
Storage Fees | 40130 | Storage Fees | Trecora Resources | 1406 | 16740 | 2025-03-01 | 2025-04-01
Storage Fees | 40130 | Storage Fees | Valero | 1 | 36672 | 2025-04-01 | 2025-05-02
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8009 | 16200 | 2025-04-01 | 2025-05-02
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1305 | 3530 | 2025-04-01 | 2025-05-02
Storage Fees | 40130 | Storage Fees | Valero | 2 | 54312 | 2025-05-25 | 2025-06-01
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8010 | 16200 | 2025-05-25 | 2025-06-01
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1306 | 3530 | 2025-05-25 | 2025-06-01
Storage Fees | 40130 | Storage Fees | Valero | 3 | 52524 | 2025-06-25 | 2025-07-02
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8011 | 16200 | 2025-06-25 | 2025-07-02
Storage Fees | 40130 | Storage Fees | USGAI Cement | 1307 | 3530 | 2025-06-25 | 2025-07-02
Storage Fees | 40130 | Storage Fees | Valero | 4 | 52104 | 2025-07-25 | 2025-07-31
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8012 | 17298 | 2025-07-25 | 2025-07-31
Storage Fees | 40130 | Storage Fees | Valero | 5 | 40524 | 2025-08-25 | 2025-08-31
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8013 | 17298 | 2025-08-25 | 2025-08-31
Storage Fees | 40130 | Storage Fees | Valero | 6 | 33310 | 2025-09-01 | 2025-09-30
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8014 | 16200 | 2025-09-01 | 2025-09-30
Storage Fees | 40130 | Storage Fees | Valero | 7 | 37510 | 2025-10-01 | 10/31/205
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8014 | 17298 | 2025-10-01 | 10/31/205
Storage Fees | 40130 | Storage Fees | Valero | 8 | 37510 | 2025-11-25 | 2025-11-30
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8015 | 17298 | 2025-11-25 | 2025-11-30
Storage Fees | 40130 | Storage Fees | Valero | 9 | 21550 | 2025-12-01 | 2025-12-31
Storage Fees | 40130 | Storage Fees | Trecora Resources | 8016 | 17298 | 2025-12-01 | 2025-12-31
|  | Storage Fees Total |  |  | 588015
Transloading Fees | 40140 | Transloading |  |  |  |  | 2024-11-01
|  | Transloading Total |  |  | 0
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1401 | 25000 | 2025-01-01 | 2025-02-01
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1501 | 25000 | 2025-02-01 | 2025-03-01
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1403 | 25000 | 2025-03-01 | 2025-04-01
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1404 | 25000 | 2025-04-01 | 2025-05-01
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1405 | 25000 | 2025-05-25 | 2025-06-01
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1406 | 25000 | 2025-06-25 | 2025-07-02
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1407 | 25000 | 2025-07-25 | 2025-07-31
Warehouse Lease Income | 40150 | Warehouse Lease | Louisiana-Pacific Corporation | 1408 | 25000 | 2025-08-25 | 2025-08-31
|  | Warehouse Lease Total |  |  | 200000
|  | Grand Total |  |  | 984858

## Current Invoice Log (OP) (hidden)
Cost Category | Cost Code # | Bank Cost Category | Cost Code Name | Vendor | Bill Number | Amount Paid | Requisition Month | Invoice Date | CURRENT REQ REPORT | DUPLICATE(S)
Travel | 60210 | Travel | Travel | Banyan Residential | Dec_25 UBS CC Reimb. | 217.32 | 2025-12-25 | 2025-12-31
|  |  | Travel Total |  |  | 217.32
Meals | 60500 | Meals | Meals | Banyan Residential | Dec_25 UBS CC Reimb. | 158.16 | 2025-12-25 | 2025-12-31
|  |  | Meals Total |  |  | 158.16
Site/Yard Maintenace | 61050 | Site/Yard Maintenace | Site/Yard Maintenace | Agri-Serv Industrial Maintenance | 788995 | 1061.6 | 2025-12-25 | 2025-12-02
|  |  | Site/Yard Maintenace Total |  |  | 1061.6
Track Repairs | 61051 | Track Repairs | Track Repairs | Mcallen Signal and Boring
|  |  | Track Repairs Total |  |  | 0
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 12325CLR | 700 | 2025-12-25 | 2025-12-10
|  |  | Crossing Repairs Total |  |  | 700
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8021 | 2500 | 2025-12-25 | 2025-12-31
|  |  | Landscape Maintenance Total |  |  | 2500
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Dec_25 UBS CC Reimb. | 1184.69 | 2025-12-25 | 2025-12-31
|  |  | Utilities Total |  |  | 1184.69
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 2698593-IN | 1952.87 | 2025-12-25 | 2025-12-03
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 2716338-IN | 2016.44 | 2025-12-25 | 2025-12-31
|  |  | Fuel Total |  |  | 3969.31
Accounting Fees | 63000 | Accounting Fees | Accounting
|  |  | Accounting Fees Total |  |  | 0
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Dec_25 UBS CC Reimb. | 1.25 | 2025-12-25 | 2025-12-31
|  |  | Professional Fees Total |  |  | 1.25
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics
|  |  | Management Fees - Hall Logistics Total |  |  | 0
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Dec_25 Management Fee | 5683.19 | 2025-12-25 | 2025-12-31
|  |  | Management Fees - Banyan Residential Total |  |  | 5683.19
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | County Line Rail Operations | Aug_25 Asset Manager Fees |  | 2025-11-01 | 2025-11-30
|  |  | AM Staff Services - Asset Manager Total |  |  | 0
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics
|  |  | Switchmen Healthcare - Reimbursable Total |  |  | 0
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Switch Yard Mowing
|  |  | Mowing Assistance Total |  |  | 0
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 34 | 11560.34 | 2025-12-25 | 2025-12-31
|  |  | Switchmen Salaries - Reimbursable Total |  |  | 11560.34
Offsite Manager | 63041 | Offsite Manager | Management Fees | County Line Rail Operations | 38 | -1603.53 | 2025-12-25 | 2025-12-31
|  |  | AM Staff Services - Accounting - Reimbursable Total |  |  | -1603.53
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 34 | 10116.6 | 2025-12-25 | 2025-12-31
|  |  | Management Fees Totals |  |  | 10116.6
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp, PC | 026
|  |  | Legal Fees - General Total |  |  | 0
Consulting Fees | 63150 | Broker Commission Fee | Broker Commission Fee | M&W Real Estate
|  |  | Consulting Fee Total |  |  | 0
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3030 | 2233.01 | 2025-12-25 | 2025-12-04
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3042 | 1337.43 | 2025-12-25 | 2025-12-11
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3054 | 1337.43 | 2025-12-25 | 2025-12-18
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3066 | 1337.43 | 2025-12-25 | 2025-12-25
|  |  | Security Expense Totals |  |  | 6245.3
Dues & Subscriptions | 67100 | Dues & Subscriptions | Dues & Subscriptions | Banyan Residential
|  |  | Dues & Subscriptions Total |  |  | 0
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Dec_25 UBS CC Reimb. | 366.67 | 2025-12-25 | 2025-12-31
|  |  | Office Expense Total |  |  | 366.67
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Dec_25 Property Tax Accrual | -7962.63 | 2025-12-25 | 2025-12-31
|  |  | Property Tax Total |  |  | -7962.63
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 4917.97 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 14284.71 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 7280.46 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 610.33 | 2025-12-25 | 2025-12-31
|  |  | Property Insurance Total |  |  | 27093.47
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Dec_25 Bank Statement
|  |  | Bank Fees Total |  |  | 0
Interest Expense | 75000 | Interest Expense | Interest Expense | Sunflower Bank
Interest Expense | 75000 | Interest Expense | Interest Expense | Sunflower Bank
Interest Expense | 75000 | Interest Expense | Interest Expense | Sunflower Bank
|  |  | Interest Expense Total |  |  | 0
Unused Fee Expense | 75005 | Unused Fee Expense | Unused Fee Expense | Sunflower Bank |  | 3285.89 | 2025-12-25 | 2025-12-31
|  |  | Unused Fee Expense Total |  |  | 3285.89
Loan Fee Expense | 75006 | Loan Fee Expense | Loan Fee Expense | Sunflower Bank | CLR Fund Loan Closing
|  |  | Loan Fee Expense Total |  |  | 0
Legal Expenditures | 75140 | Legal Expenditures | Condemnation Expense | Cherry Peterson Albert LLC | 134912
|  |  | Condemnation Expense Total |  |  | 0
|  |  | Grand Total |  |  | 64577.63 |  |  | TRUE

## Prior Invoice Log (OP) (hidden)
Cost Category | Cost Code # | Bank Cost Category | Cost Code Name | Vendor | Bill Number | Amount Paid | Requisition Month | Invoice Date | CURRENT REQ REPORT | DUPLICATE(S)
Travel | 60210 | Travel | Travel | Banyan Residential | Jan_25 UBS CC Trx | 154.1 | 2025-01-25 | 2025-01-31
Travel | 60210 | Travel | Travel | Banyan Residential | Dillon Schroeder Mileage (February) | 50.25 | 2025-02-01 | 2025-02-28
Travel | 60210 | Travel | Travel | Banyan Residential | Feb_25 CC Exp | 50.23 | 2025-02-01 | 2025-02-28
Travel | 60210 | Travel | Travel | Banyan Residential | Mar_25 CC Reimbursement | 120.97 | 2025-03-01 | 2025-03-31
Travel | 60210 | Travel | Travel | Dillon Schroeder | Mar_25 Mileage Reimb. | 75 | 2025-03-01 | 2025-03-31
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Feb) | 322 | 2025-04-01 | 2025-04-01
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Mar) | 161 | 2025-04-01 | 2025-04-01
Travel | 60210 | Travel | Travel | Banyan Residential | Apr_25 UBS CC Reimbursement | 1048.73 | 2025-04-01 | 2025-04-23
Travel | 60210 | Travel | Travel | Banyan Residential | Dillon Schroeder Mileage (May) | 154 | 2025-05-25 | 2025-05-31
Travel | 60210 | Travel | Travel | Banyan Residential | Dillon Schroeder Mileage (June) | 319.2 | 2025-06-25 | 2025-06-30
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Juen) | 161 | 2025-06-25 | 2025-06-30
Travel | 60210 | Travel | Travel | Banyan Residential | June 2025 UBS Credit Card Reimb | 959.28 | 2025-06-25 | 2025-06-30
Travel | 60210 | Travel | Travel | Banyan Residential | Jul_25 UBS CC Reimb. | 343.51 | 2025-07-01 | 2025-07-31
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (July'25) | 161 | 2025-08-01 | 2025-08-01
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Aug'25) | 161 | 2025-08-01 | 2025-08-31
Travel | 60210 | Travel | Travel | Banyan Residential | Aug_25 UBS CC (Travel) | 146.61 | 2025-08-01 | 2025-08-08
Travel | 60210 | Travel | Travel | Banyan Residential | Sep_25 UBS CC | 578.17 | 2025-09-25 | 2025-09-22
Travel | 60210 | Travel | Travel | Banyan Residential | Oct_25 UBS CC | 536.05 | 2025-10-01 | 2025-10-31
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Sep_25) | 161 | 2025-10-01 | 2025-10-01
Travel | 60210 | Travel | Travel | Banyan Residential | Jay Kennedy Mileage (Oct_25) | 161 | 2025-10-01 | 2025-10-16
Travel | 60210 | Travel | Travel | Banyan Residential | Dillon Schroeder Mileage (Nov_25) | 453.6 | 2025-11-01 | 2025-11-30
Travel | 60210 | Travel | Travel | Banyan Residential | Nov_25 UBS CC Reimb. | 1249.63 | 2025-11-01 | 2025-11-30
Travel | 60210 | Travel | Travel | Banyan Residential | Dec_25 UBS CC Reimb. | 217.32 | 2025-12-25 | 2025-12-31
|  |  | Travel Total |  |  | 7744.65
Meals | 60500 | Meals | Meals | Banyan Residential | Jul_25 UBS CC Reimb. | 59.22 | 2025-07-01 | 2025-07-31
Meals | 60500 | Meals | Meals | Banyan Residential | Sep_25 UBS CC | 95.48 | 2025-09-25 | 2025-09-22
Meals | 60500 | Meals | Meals | Banyan Residential | Oct_25 UBS CC | 62.45 | 2025-10-01 | 2025-10-31
Meals | 60500 | Meals | Meals | Banyan Residential | Nov_25 UBS CC Reimb. | 171.23 | 2025-11-01 | 2025-11-30
Meals | 60500 | Meals | Meals | Banyan Residential | Dec_25 UBS CC Reimb. | 158.16 | 2025-12-25 | 2025-12-31
|  |  | Meals Total |  |  | 546.54
Site/Yard Maintenace | 61050 | Site/Yard Maintenace | Site/Yard Maintenace | Biskamp Electric, Inc | 550086-1 | 4239.07 | 2025-07-01 | 2025-07-11
Site/Yard Maintenace | 61050 | Site/Yard Maintenace | Site/Yard Maintenace | Banyan Residential | Oct_25 UBS CC | 1798 | 2025-10-01 | 2025-10-31
Site/Yard Maintenace | 61050 | Site/Yard Maintenace | Site/Yard Maintenace | Kauffman Co. | I2510-34 | 346 | 2025-11-01 | 2025-11-20
Site/Yard Maintenace | 61050 | Site/Yard Maintenace | Site/Yard Maintenace | Agri-Serv Industrial Maintenance | 788995 | 1061.6 | 2025-12-25 | 2025-12-02
|  |  | Site/Yard Maintenance Total |  |  | 7444.67
Track Repairs | 61051 | Track Repairs | Track Repairs | Mcallen Signal and Boring | 11025 | 1775 | 2025-01-25 | 2025-01-14
|  |  | Track Repairs Total |  |  | 1775
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 1525CLR | 700 | 2025-01-25 | 2025-01-13
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 12925CLR | 764 | 2025-02-01 | 2025-02-04
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 22825CLR | 700 | 2025-03-01 | 2025-03-05
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 33125CLR | 700 | 2025-04-01 | 2025-04-09
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 42625CLR | 700 | 2025-05-25 | 2025-05-01
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 52225CLR | 700 | 2025-05-25 | 2025-05-28
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 61925CLR | 700 | 2025-06-25 | 2025-06-25
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 71725CLR | 700 | 2025-07-01 | 2025-07-23
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 81425CLR | 700 | 2025-08-01 | 2025-08-27
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 91125CLR | 700 | 2025-09-25 | 2025-09-16
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 101425CLR | 700 | 2025-10-01 | 2025-10-17
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 11425CLR | 700 | 2025-11-01 | 2025-11-04
Crossing Repairs | 61052 | Crossing Repairs | Crossing Repairs | Mcallen Signal and Boring | 12325CLR | 700 | 2025-12-25 | 2025-12-10
|  |  | Crossing Repairs Total |  |  | 9164
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8005 | 2500 | 2025-09-25 | 2025-09-02
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8009 | 2500 | 2025-09-25 | 2025-09-30
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8013 | 2500 | 2025-10-01 | 2025-10-31
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8017 | 2500 | 2025-11-01 | 2025-11-30
Landscape Maintenance | 61056 | Landscape Maintenance | Landscape Maintenance | Switch Yard Mowing | 8021 | 2500 | 2025-12-25 | 2025-12-31
|  |  | Landscape Maintenance Total |  |  | 12500
Utilities | 61150 | Utilities | Utilities | Entergy Services | Jan_25 UBS CC Trx | 113.89 | 2025-01-25 | 2025-01-31
Utilities | 61150 | Utilities | Utilities | Live Oak Environmental | Jan_25 UBS CC Trx | 120.97 | 2025-01-25 | 2025-01-31
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Feb_25 CC Exp | 496.99 | 2025-02-01 | 2025-02-28
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Apr_25 UBS CC Reimbursement | 120.97 | 2025-04-01 | 2025-04-23
Utilities | 61150 | Utilities | Utilities | Entergy Services, LLC | Apr_2025 Bill Pay | 113.15 | 2025-04-01 | 2025-04-23
Utilities | 61150 | Utilities | Utilities | Entergy Services, LLC | Apr_2025 Bill Pay | 3451.19 | 2025-04-01 | 2025-04-24
Utilities | 61150 | Utilities | Utilities | Banyan Residential | May_25 UBS CC Reimbursement | 120.97 | 2025-05-25 | 2025-05-07
Utilities | 61150 | Utilities | Utilities | Banyan Residential | June_25 UBS CC Reimbursement | 367.1 | 2025-06-25 | 2025-06-30
Utilities | 61150 | Utilities | Utilities | Entergy Services | June 2025 Bill Pay | 118.6 | 2025-06-25 | 2025-06-03
Utilities | 61150 | Utilities | Utilities | Entergy Services | July Bill Pay | 238.46 | 2025-07-01 | 2025-07-10
Utilities | 61150 | Utilities | Utilities | Entergy Services | July Bill Pay | 5516.43 | 2025-07-01 | 2025-07-10
Utilities | 61150 | Utilities | Utilities | Entergy Services | July Bill Pay | 121.18 | 2025-07-01 | 2025-07-31
Utilities | 61150 | Utilities | Utilities | Entergy Services | July Bill Pay | 5506.03 | 2025-07-01 | 2025-07-31
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Jul_25 UBS CC Reimb. | 120.97 | 2025-07-01 | 2025-07-31
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Aug_25 UBS CC (Travel) | 120.97 | 2025-08-01 | 2025-08-08
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Aug_25 UBS CC 2 | 374.84 | 2025-09-25 | 2025-09-01
Utilities | 61150 | Utilities | Utilities | CITY OF SILSBEE WATER SERVICE | 040875000Sep25 | 460.84 | 2025-09-25 | 2025-09-18
Utilities | 61150 | Utilities | Utilities | CITY OF SILSBEE WATER SERVICE | 040875000Oct25 | 308.32 | 2025-09-25 | 2025-09-30
Utilities | 61150 | Utilities | Utilities | Entergy | Entergy Bill Pay | 116.93 | 2025-09-25 | 2025-09-05
Utilities | 61150 | Utilities | Utilities | Entergy | Entergy Bill Pay | 5481.58 | 2025-09-25 | 2025-09-18
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Sep_25 UBS CC | 120.97 | 2025-09-25 | 2025-09-22
Utilities | 61150 | Utilities | Utilities | Entergy | Entergy Bill Pay | 116.93 | 2025-10-01 | 2025-10-06
Utilities | 61150 | Utilities | Utilities | Entergy | Entergy Bill Pay | 5481.58 | 2025-10-01 | 2025-10-16
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Oct_25 UBS CC | 120.97 | 2025-10-01 | 2025-10-16
Utilities | 61150 | Utilities | Utilities | Entergy | Nov_25 Entergy Bill Pay | 122.33 | 2025-11-01 | 2025-11-10
Utilities | 61150 | Utilities | Utilities | Entergy | Nov_25 Entergy Bill Pay | 5539.4 | 2025-11-01 | 2025-11-10
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Nov_25 UBS CC Reimb. | 120.97 | 2025-11-01 | 2025-11-30
Utilities | 61150 | Utilities | Utilities | Banyan Residential | Dec_25 UBS CC Reimb. | 1184.69 | 2025-12-25 | 2025-12-31
|  |  | Utilities Total |  |  | 36198.22
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 2460529-IN | 883.52 | 2025-01-25 | 2025-01-15
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 09102025 | 3701.52 | 2025-09-25 | 2025-09-10
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 2698593-IN | 1952.87 | 2025-12-25 | 2025-12-03
Fuel | 61164 | Fuel | Fuel | Great Lakes Petroleum | 2716338-IN | 2016.44 | 2025-12-25 | 2025-12-31
|  |  | Fuel Total |  |  | 8554.35
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251010001 | 4709.25 | 2025-01-25 | 2025-01-10
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251077411 | 6914.25 | 2025-02-01 | 2025-02-20
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251127676 | 8121.75 | 2025-03-01 | 2025-03-31
Accounting Fees | 63000 | Accounting Fees | Accounting | Forvis Mazars | 2427642 | 4068.75 | 2025-03-01 | 2025-03-31
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251199460 | 4498.2 | 2025-04-01 | 2025-04-11
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251128058 | 1192 | 2025-05-25 | 2025-03-11
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251307424 | 8526.75 | 2025-05-25 | 2025-05-14
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251307617 | 149 | 2025-05-25 | 2025-05-15
Accounting Fees | 63000 | Accounting Fees | Accounting | Forvis Mazars | 2526026 | 4068.75 | 2025-05-25 | 2025-05-06
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251430364 | 4901.25 | 2025-07-01 | 2025-07-21
Accounting Fees | 63000 | Accounting Fees | Accounting | CliftonLarsonAllen LLP | L251526216 | 4941.43 | 2025-08-01 | 2025-08-28
|  |  | Accounting Fees Total |  |  | 52091.38
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Feb_25 CC Exp | 253.33 | 2025-02-01 | 2025-02-28
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | June_25 UBS CC Reimbursement | 58.69 | 2025-06-25 | 2025-06-30
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Jul_25 UBS CC Reimb. | 67.77 | 2025-07-01 | 2025-07-31
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Jul_25 UBS CC Reimb. | 999.99 | 2025-08-01 | 2025-08-31
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Aug_25 UBS CC (Travel) | 142.22 | 2025-08-01 | 2025-08-08
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | DMA, Inc. | 2500 | 2025-08-01 | 2025-07-17
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Aug_25 UBS CC 3 | 115 | 2025-09-25 | 2025-09-01
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Aug_25 UBS CC 3 | 94.79 | 2025-09-25 | 2025-09-01
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Sep_25 UBS CC | 227.07 | 2025-09-25 | 2025-09-22
Professional Fees | 63025 | Professional Fees | Professional Fees | CSRS | 55515CLRF (Paid by County Line Rail Fund) | 1960 | 2025-10-01 | 2025-10-31
Professional Fees | 63025 | Professional Fees | Professional Fees | Hardin County | 2510036 | 425 | 2025-11-01 | 2025-11-18
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Nov_25 UBS CC Reimb. | 296.26 | 2025-11-01 | 2025-11-30
Professional Fees | 63025 | Professional Fees | Professional Fees | Banyan Residential | Dec_25 UBS CC Reimb. | 1.25 | 2025-12-25 | 2025-12-31
|  |  | Professional Fees Total |  |  | 7141.37
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2029 | 2895.77 | 2025-01-25 | 2025-01-07
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2031 | 2895.77 | 2025-02-01 | 2025-02-10
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2033 | 2943.27 | 2025-03-01 | 2025-03-31
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2035 | 3106.5 | 2025-04-01 | 2025-04-19
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2037 | 8496.5 | 2025-05-25 | 2025-05-06
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2039 | 8667.5 | 2025-06-25 | 2025-06-05
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2041 | 8428.2 | 2025-07-01 | 2025-07-09
Management Fees - Hall Logistics | 63026 | Management Fees - Hall Logistics | Management Fees - Hall Logistics | Hall Rail Logistics | 2043 | 8206.5 | 2025-08-01 | 2025-08-22
|  |  | Management Fees - Hall Logistics Total |  |  | 45640.01
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Jan25 Fees | 12500 | 2025-01-25 | 2025-01-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Feb_25 Management Fees | 12500 | 2025-02-01 | 2025-02-28
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Mar_25 Management Fees | 12500 | 2025-03-01 | 2025-03-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Apr_25 Management Fee | 12500 | 2025-04-01 | 2025-04-30
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | May_25 Management Fee | 12500 | 2025-05-25 | 2025-05-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Juney_25 Management Fee | 12500 | 2025-06-25 | 2025-06-30
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | July_25 Management Fee | 12500 | 2025-07-01 | 2025-07-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Aug_25 Management Fee | 5683.19 | 2025-08-01 | 2025-08-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC |  | 5683.19 | 2025-09-25 | 2025-09-30
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Oct_25 Management Fee | 5683.19 | 2025-10-01 | 2025-10-31
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Nov_25 Management Fee | 5683.19 | 2025-11-01 | 2025-11-30
AM Fees - Banyan | 63027 | Management Fees - Banyan Residential | Management Fees - Banyan Residential | Banyan Residential LLC | Dec_25 Management Fee | 5683.19 | 2025-12-25 | 2025-12-31
|  |  | Management Fees - Banyan Residential Total |  |  | 115915.95
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | Jan25 Fees | 1875 | 2025-01-25 | 2025-01-31
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | Feb_25 Asset Manager Fees | 1875 | 2025-02-01 | 2025-02-28
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | Mar_25 Asset Manager Fees | 1875 | 2025-03-01 | 2025-03-31
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | Apr_25 Asset Manager Fees | 1875 | 2025-04-01 | 2025-04-30
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | May_25 Asset Manager Fees | 1875 | 2025-05-25 | 2025-05-31
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | June_25 Asset Manager Fees | 1875 | 2025-06-25 | 2025-06-30
Asset Manager - (County Line) | 63028 | Asset Manager - (County Line) | AM Staff Services - Asset Manager | Banyan Residential LLC | July_25 Asset Manager Fees | 1875 | 2025-07-01 | 2025-07-31
|  |  | AM Staff Services - Asset Manager Total |  |  | 13125
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2030 | 1807.07 | 2025-01-25 | 2025-01-01
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2032 | 1807.07 | 2025-01-25 | 2025-01-27
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2034 | 1807.07 | 2025-02-01 | 2025-02-26
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2036 | 1807.07 | 2025-03-01 | 2025-03-31
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2038 | 1807.07 | 2025-04-01 | 2025-04-23
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2040 | 1807.07 | 2025-05-25 | 2025-05-24
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2042 | 1807.07 | 2025-06-25 | 2025-06-19
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2044 | 1807.07 | 2025-07-01 | 2025-07-18
Switchmen Salaries - Reimbursable | 63032 | Switchmen Healthcare – Reimbursable | Switchmen Healthcare – Reimbursable | Hall Rail Logistics | 2046 | 1807.07 | 2025-08-01 | 2025-08-03
|  |  | Switchmen Salaries - Reimbursable Total |  |  | 16263.63
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402095 | 1350 | 2025-01-25 | 2025-01-20
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402058 | 1350 | 2025-01-25 | 2025-01-07
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402429 | 1350 | 2025-03-01 | 2025-03-31
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402475 | 2700 | 2025-04-01 | 2025-04-02
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402663 | 2700 | 2025-04-01 | 2025-04-30
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Southern Lawn & Landscapes | 402822 | 2700 | 2025-05-25 | 2025-05-28
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Hall Rail Logistics | 2041 | 2500 | 2025-07-01 | 2025-07-09
Mowing Assistance - Reimbursable | 63033 | Mowing Assistance - Reimbursable | Mowing Assistance | Switch Yard Mowing | 8001 | 2500 | 2025-08-01 | 2025-08-07
|  |  | Mowing Assistance Total |  |  | 17150
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2030 | 10070 | 2025-01-25 | 2025-01-01
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2032 | 15480 | 2025-01-25 | 2025-01-27
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2034 | 9600 | 2025-02-01 | 2025-02-26
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2036 | 9600 | 2025-03-01 | 2025-03-31
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2038 | 9780 | 2025-04-01 | 2025-04-23
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2040 | 9888 | 2025-05-25 | 2025-05-24
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2042 | 10718.88 | 2025-06-25 | 2025-06-19
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2044 | 11900.29 | 2025-07-01 | 2025-07-18
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | Hall Rail Logistics | 2046 | 4944 | 2025-08-01 | 2025-08-03
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 2 | 10970.76 | 2025-08-01 | 2025-08-31
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 10 | 10888.12 | 2025-09-25 | 2025-09-30
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 18 | 10981.73 | 2025-10-01 | 2025-10-31
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 26 | 10910.92 | 2025-11-01 | 2025-11-30
Switchmen Salaries - Reimbursable | 63034 | Switchmen Salaries - Reimbursable | Switchmen Salaries - Reimbursable | County Line Rail Operations | 34 | 11560.34 | 2025-12-25 | 2025-12-31
|  |  | Switchmen Salaries - Reimbursable Total |  |  | 147293.04
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | Jan25 Fees | 1875 | 2025-01-25 | 2025-01-31
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | Feb_25 Staff Accounting Fees | 1875 | 2025-02-01 | 2025-02-28
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | Mar_25 Accounting | 1875 | 2025-03-01 | 2025-03-31
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | Apr_25 Staff Accounting Fee | 1875 | 2025-04-01 | 2025-04-30
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | May_25 Staff Accounting Fee | 1875 | 2025-05-25 | 2025-05-31
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | June_25 Staff Accounting Fee | 1875 | 2025-06-25 | 2025-06-30
Accounting (County Line) | 63036 | Accounting (County Line) | AM Staff Services - Accounting - Reimbursable | Banyan Residential LLC | July_25 Staff Accounting Fee | 1875 | 2025-07-01 | 2025-07-31
|  |  | AM Staff Services - Accounting - Reimbursable Total |  |  | 13125
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | Jan25 Fees | 5000 | 2025-01-25 | 2025-01-31
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | Feb_25 Bus Dev Fee | 5000 | 2025-02-01 | 2025-02-28
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | Mar_25 Business Dev Fee | 5000 | 2025-03-01 | 2025-03-31
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | Apr_25 Business Dev Fee | 5000 | 2025-04-01 | 2025-04-30
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | May_25 Business Dev Fee | 5000 | 2025-05-25 | 2025-05-31
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | June_25 Business Dev Fee | 5000 | 2025-06-25 | 2025-06-30
Business Development (County Line) | 63040 | Business Development (County Line) | AM Staff Services - Bus Dev - Reimbursable | Banyan Residential LLC | July_25 Business Dev Fee | 5000 | 2025-07-01 | 2025-07-31
|  |  | AM Staff Services - Bus Dev - Reimbursable Total |  |  | 35000
Offsite Manager | 63041 | Offsite Manager | Management Fees | County Line Rail Operations | 6 | 7727 | 2025-09-25 | 2025-09-01
Offsite Manager | 63041 | Offsite Manager | Management Fees | County Line Rail Operations | 14 | 6650.05 | 2025-10-01 | 2025-10-01
Offsite Manager | 63041 | Offsite Manager | Management Fees | County Line Rail Operations | 22 | 5818.6 | 2025-10-01 | 2025-10-31
Offsite Manager | 63041 | Offsite Manager | Management Fees | County Line Rail Operations | 38 | -1603.53 | 2025-12-25 | 2025-12-31 | - Reimbursement from December Insurance Allocation
|  |  | AM Staff Services - Accounting - Reimbursable Total |  |  | 18592.12
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 2 | 13142.97 | 2025-08-01 | 2025-08-31
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 10 | 13142.97 | 2025-09-25 | 2025-09-30
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 18 | 13142.97 | 2025-10-01 | 2025-10-31
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 26 | 1584.52 | 2025-11-01 | 2025-11-30
Offsite Staff | 63042 | Offsite Staff | Offsite Staff | County Line Rail Operations | 34 | 10116.6 | 2025-12-25 | 2025-12-31
|  |  | Offsite Staff Total |  |  | 51130.03
Legal Fees | 63050 | Legal Fees | Legal Fees - General | MeHaffy Weber | 732951 | 1231 | 2025-01-25 | 2024-12-13
Legal Fees | 63050 | Legal Fees | Legal Fees - General | CT Corporation | 26454021-RI | 1261.7 | 2025-01-25 | 2023-04-20
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Troutman Pepper Locke | 131892561 | 1105 | 2025-01-25 | 2025-01-28
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp | 012 | 45.75 | 2025-02-01 | 2025-02-19
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp | 013 | 1006.5 | 2025-03-01 | 2025-03-11
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp | 017 | 1647 | 2025-04-01 | 2025-04-16
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Akerman LLP | 9947182 | 6577.5 | 2025-05-25 | 2024-01-16
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp, PC | 018 | 2287.5 | 2025-05-25 | 2025-05-12
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17986CLRF | 2823.75 | 2025-05-25 | 2025-05-21
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 16946CLRF | 1626.25 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17261CLRF | 5483.38 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17389CLRF | 3710 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17855CLRF | 843.75 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 15958CLRF | 748.13 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 16802CLRF | 1960 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17084CLRF | 4407 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17493CLRF | 798.75 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law (Paid by CLRF) | 17699CLRF | 4650 | 2025-04-01 | 2025-04-01 | - Recorded on the April 2025 FS
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp | 019 | 2470.5 | 2025-06-25 | 2025-06-10
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp | 021 | 457.5 | 2025-07-01 | 2025-07-15
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Akerman LLP | 10091994 | 9301.5 | 2025-07-01 | 2025-07-15
Legal Fees | 63050 | Legal Fees | Legal Fees - General | CT Corporation | 34966772-RI | 187 | 2025-08-01 | 2025-05-07
Legal Fees | 63050 | Legal Fees | Legal Fees - General | CT Corporation | 5009049986-01 | 510.2 | 2025-08-01 | 2025-03-01
Legal Fees | 63050 | Legal Fees | Legal Fees - General | CT Corporation | 509050026-01 | 720.4 | 2025-08-01 | 2025-03-01
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp, PC | 023 | 2104.5 | 2025-10-01 | 2025-10-08
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law | 18109CLRF (Paid by Couny Line Rail Fund) | 4012.5 | 2025-10-01 | 2025-10-01
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Novos Law | 18292CLRF (Paid by Couny Line Rail Fund) | 3921.25 | 2025-10-01 | 2025-10-01
Legal Fees | 63050 | Legal Fees | Legal Fees - General | Patrick M Knapp, PC | 026 | 732 | 2025-11-01 | 2025-11-10
|  |  | Legal Fees - General Total |  |  | 66630.31
Consulting Fees | 63100 | Consulting Fees | Consulting Fee | Access Surveyors LLC | 2024941-1 | 5390.85 | 2025-04-01 | 2025-04-11
Consulting Fees | 63100 | Consulting Fees | Consulting Fee | ESE Patners LLC | 22-2000-21 | 2950 | 2025-05-25 | 2025-05-27
|  |  | Consulting Fee Total |  |  | 8340.85
Consulting Fees | 63150 | Broker Commission Fee | Broker Commission Fee | M&W Real Estate | 18 | 9535.41 | 2025-07-01 | 2025-07-10
|  |  | Broker Commission Fee Total |  |  | 9535.41
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2466 | 2233.01 | 2025-01-25 | 2025-01-02
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2469 | 1337.43 | 2025-01-25 | 2025-01-09
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2487 | 1337.43 | 2025-01-25 | 2025-01-16
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2493 | 1337.43 | 2025-01-25 | 2025-01-23
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2510 | 1385.22 | 2025-01-25 | 2025-01-30
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2521 | 2137.43 | 2025-02-01 | 2025-02-06
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2526 | 1337.43 | 2025-02-01 | 2025-02-13
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2544 | 1337.43 | 2025-02-01 | 2025-02-20
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2556 | 1337.43 | 2025-02-01 | 2025-02-27
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2567 | 2137.43 | 2025-03-01 | 2025-03-06
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2578 | 1337.43 | 2025-03-01 | 2025-03-15
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2590 | 1337.43 | 2025-03-01 | 2025-03-27
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2601 | 1337.43 | 2025-04-01 | 2025-04-01
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2613 | 2137.43 | 2025-04-01 | 2025-04-03
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2624 | 1337.43 | 2025-04-01 | 2025-04-10
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2635 | 1337.43 | 2025-04-01 | 2025-04-17
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2646 | 1433.01 | 2025-04-01 | 2025-04-24
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2657 | 2137.43 | 2025-05-25 | 2025-05-01
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2668 | 1337.43 | 2025-05-25 | 2025-05-08
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2679 | 1337.43 | 2025-05-25 | 2025-05-15
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2691 | 1337.43 | 2025-05-25 | 2025-05-22
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2702 | 1442.57 | 2025-05-25 | 2025-05-29
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2703 | 1442.57 | 2025-06-25 | 2025-06-01
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2713 | 1337.43 | 2025-06-25 | 2025-06-05
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2724 | 2137.43 | 2025-06-25 | 2025-06-12
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2737 | 1337.43 | 2025-06-25 | 2025-06-19
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2749 | 1337.43 | 2025-06-25 | 2025-06-26
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2762 | 2137.43 | 2025-07-01 | 2025-07-03
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2774 | 1433.01 | 2025-07-01 | 2025-07-10
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2786 | 1337.43 | 2025-07-01 | 2025-07-17
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2798 | 1433.01 | 2025-07-01 | 2025-07-24
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2810 | 1349.38 | 2025-07-01 | 2025-07-31
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2822 | 2137.43 | 2025-08-01 | 2025-08-07
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2834 | 1337.43 | 2025-08-01 | 2025-08-14
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2846 | 1337.43 | 2025-08-01 | 2025-08-21
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2858 | 1433.01 | 2025-08-01 | 2025-08-28
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2870 | 2271.25 | 2025-09-25 | 2025-09-04
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2882 | 1433.01 | 2025-09-25 | 2025-09-11
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2894 | 1337.43 | 2025-09-25 | 2025-09-18
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2908 | 1337.43 | 2025-09-25 | 2025-09-25
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2920 | 2137.43 | 2025-10-01 | 2025-10-02
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2932 | 1337.43 | 2025-10-01 | 2025-10-09
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2945 | 1337.43 | 2025-10-01 | 2025-10-16
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2957 | 1337.43 | 2025-10-01 | 2025-10-23
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2969 | 1528.6 | 2025-10-01 | 2025-10-30
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2982 | 2233.01 | 2025-11-01 | 2025-11-06
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 2994 | 1337.43 | 2025-11-01 | 2025-11-13
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3006 | 1528.6 | 2025-11-01 | 2025-11-20
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3018 | 1337.43 | 2025-11-01 | 2025-11-27
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3030 | 2233.01 | 2025-12-25 | 2025-12-04
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3042 | 1337.43 | 2025-12-25 | 2025-12-11
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3054 | 1337.43 | 2025-12-25 | 2025-12-18
Security | 64000 | Security Expense | Security Expense | Tower Security Company | 3066 | 1337.43 | 2025-12-25 | 2025-12-25
|  |  | Security Expense Totals |  |  | 82034.61
Dues & Subscriptions | 67100 | Dues & Subscriptions | Dues & Subscriptions | Banyan Residential | Mar_25 CC Reimbursement | 1560 | 2025-03-01 | 2025-03-31
|  |  | Dues & Subscriptions Total |  |  | 1560
Office Expense | 67200 | Office Expense | Office Expense | Google | Jan_25 UBS CC Trx | 146.56 | 2025-01-25 | 2025-01-31
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Mar_25 CC Reimbursement | 1336.47 | 2025-03-01 | 2025-03-31
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Apr_25 UBS CC Reimbursement | 155.05 | 2025-04-01 | 2025-04-23
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | May_25 UBS CC Reimbursement | 173.62 | 2025-05-25 | 2025-05-07
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Sep_25 UBS CC | 438.61 | 2025-09-25 | 2025-09-22
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Oct_25 UBS CC | 373.16 | 2025-10-01 | 2025-10-31
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Nov_25 UBS CC Reimb. | 109.51 | 2025-11-01 | 2025-11-30
Office Expense | 67200 | Office Expense | Office Expense | Banyan Residential | Dec_25 UBS CC Reimb. | 366.67 | 2025-12-25 | 2025-12-31
|  |  | Office Expense Total |  |  | 3099.65
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Jan_25 Accrual | 9609.65 | 2025-01-25 | 2025-01-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Feb_25 Property Tax Accrual | 9609.65 | 2025-02-01 | 2025-02-28
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Mar_25 Property Tax Accrual | 9609.65 | 2025-03-01 | 2025-03-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Apr_25 Property Tax Accrual | 9609.65 | 2025-04-01 | 2025-04-30
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | May_25 Property Tax Accrual | 9609.65 | 2025-05-25 | 2025-05-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | June_25 Property Tax Accrual | 9609.65 | 2025-06-25 | 2025-06-30
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | July_25 Property Tax Accrual | 9609.65 | 2025-07-01 | 2025-07-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Aug_25 Property Tax Accrual | 9609.65 | 2025-08-01 | 2025-08-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Sep_25 Property Tax Accrual | 9609.65 | 2025-09-25 | 2025-09-30
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Oct_25 Property Tax Accrual | 9609.65 | 2025-10-01 | 2025-10-31
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Nov_25 Property Tax Accrual | 9609.65 | 2025-11-01 | 2025-11-30
Property Tax | 68050 | Property Tax | Property Tax | DMA, Inc. | Dec_25 Property Tax Accrual | -7962.63 | 2025-12-25 | 2025-12-31
|  |  | Property Tax Total |  |  | 97743.52
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Jan_25 Accrual | 6542.08 | 2025-01-25 | 2025-01-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Feb_25 Accrual | 6542.08 | 2025-02-01 | 2025-02-28
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Mar_25 Pre-paid Insurance | 6542.08 | 2025-03-01 | 2025-03-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Apr_25 Pre-paid Insurance | 6542.08 | 2025-04-01 | 2025-04-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | May_25 Pre-paid Insurance | 14490.72 | 2025-05-25 | 2025-05-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | June_25 Pre-paid Insurance | 14490.72 | 2025-06-25 | 2025-06-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | July_25 Pre-paid Insurance | 14490.72 | 2025-07-01 | 2025-07-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Aug_25 Pre-paid Insurance | 6542.04 | 2025-08-01 | 2025-08-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Aug_25 Pre-paid Insurance | 7948.64 | 2025-08-01 | 2025-08-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Aug_25 Pre-paid Insurance | 4917.97 | 2025-08-01 | 2025-08-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Aug_25 Pre-paid Insurance | 14284.71 | 2025-08-01 | 2025-08-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | 509037 (Reallocated from CLIP) | 601.76 | 2025-09-25 | 2025-09-01
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | 520084 (Reallocated from CLIP) | 1759.14 | 2025-09-25 | 2025-09-01
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | 523498 (Reallocated from CLIP) | 1524.46 | 2025-09-25 | 2025-09-01
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Sep_25 Insurance Accrual | 4917.97 | 2025-09-25 | 2025-09-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Sep_25 Insurance Accrual | 7948.64 | 2025-09-25 | 2025-09-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Sep_25 Insurance Accrual | 14284.71 | 2025-09-25 | 2025-09-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Sep_25 Insurance Accrual (CLIP Reallocation) | 7280.46 | 2025-09-25 | 2025-09-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Oct_25 Insurance Accrual | 7948.65 | 2025-10-01 | 2025-10-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Oct_25 Insurance Accrual | 4917.97 | 2025-10-01 | 2025-10-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Oct_25 Insurance Accrual | 14284.71 | 2025-10-01 | 2025-10-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Oct_25 Insurance Accrual (CLIP Reallocation) | 7280.46 | 2025-10-01 | 2025-10-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Nov_25 Insurance Accrual | 4917.97 | 2025-11-01 | 2025-11-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Nov_25 Insurance Accrual | 14284.71 | 2025-11-01 | 2025-11-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Nov_25 Insurance Accrual | 7280.46 | 2025-11-01 | 2025-11-30
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 4917.97 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 14284.71 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 7280.46 | 2025-12-25 | 2025-12-31
Property Insurance | 68055 | Property Insurance | Property Insurance | Pre-paid property insurance | Dec_25 Insurance Accrual | 610.33 | 2025-12-25 | 2025-12-31
|  |  | Property Insurance Total |  |  | 229659.38
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Mar_25 Bank Fee | 38.78 | 2025-03-01 | 2025-03-31
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Apr_25 Bank Fee | 62.85 | 2025-04-01 | 2025-04-30
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | May_25 Bank Fee | 94.69 | 2025-05-25 | 2025-05-31
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | June_25 Bank Fee | 81.99 | 2025-06-25 | 2025-06-11
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | July_25 Bank Fee | 105.18 | 2025-07-01 | 2025-07-31
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Aug_25 Account Analysis Charge | 26.31 | 2025-08-01 | 2025-08-29
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Sep_25 Bank Statement | 78.29 | 2025-09-25 | 2025-09-11
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Oct_25 Bank Statement | 207.29 | 2025-10-01 | 2025-10-24
Bank Fees | 68110 | Bank Fees | Bank Fees | Veritex Community Bank | Nov_25 Bank Statement | 214.62 | 2025-11-01 | 2025-11-17
|  |  | Bank Fees Total |  |  | 910
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | Jan25 Interest | 23429.39 | 2025-01-25 | 2025-01-31
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | Feb_25 Accrued Interest | 21202.81 | 2025-02-21 | 2025-02-21
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | Mar_25 Interest | 23498.35 | 2025-03-01 | 2025-03-21
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | Apr_25 Interest | 22736.4 | 2025-04-01 | 2025-04-30
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | May_25 Interest | 23534.89 | 2025-05-25 | 2025-05-31
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | June_25 Interest | 22714.3 | 2025-06-25 | 2025-06-25
Interest Expense | 75000 | Interest Expense | Interest Expense | Veritex Community Bank | July_25 Interest | 23581.94 | 2025-07-01 | 2025-07-31
|  |  | Interest Expense Total |  |  | 160698.08
Unused Fee Expense | 75005 | Unused Fee Expense | Unused Fee Expense | Sunflower Bank | CLR Fund Loan Closing | 667.68 | 2025-09-25 | 2025-09-30
Unused Fee Expense | 75005 | Unused Fee Expense | Unused Fee Expense | Sunflower Bank |  | 3285.89 | 2025-12-25 | 2025-12-31
|  |  | Unused Fee Expense Total |  |  | 3953.57
Legal Expenditures | 75140 | Legal Expenditures | Condemnation Expense | Cherry Peterson Albert LLC | 131842 | 1022.5 | 2025-01-25 | 2024-12-31
Legal Expenditures | 75140 | Legal Expenditures | Condemnation Expense | Cherry Peterson Albert LLC | 132427 | 1392.45 | 2025-03-01 | 2025-03-21
Legal Expenditures | 75140 | Legal Expenditures | Condemnation Expense | Cherry Peterson Albert LLC | 132713 | 204.5 | 2025-04-01 | 2025-03-31
Legal Expenditures | 75140 | Legal Expenditures | Condemnation Expense | Cherry Peterson Albert LLC | 134912 | 1264 | 2025-11-01 | 2025-11-30
|  |  | Condemnation Expense Total |  |  | 3883.45
|  |  | Grand Total |  |  | 1284443.79

## Bridge Approvd Budget to Actual (hidden)
PROJECT FUNDING REQUISITION
Bishop Arts JV, LLC
Application Period: 12/31/21
Requisition: #14
|  |  | Bishop Arts | Previous Contingency | Current Contingency | Bishop Arts | Previous Application | Payment this period | Total Complete & Draw To Date |  | Balance remaining
Yardi Code | COA# | Account Name | Approved JV Budget | Funding & Reallocation | Funding & Reallocation | Current Approved Budget | Inception to 11/30/21 | 12/31/21 | Incurred to 12/31/21 | Percent Drawn | As of 12/31/21
1470005 | 11010 | Land Purchase | 5858494.36 | 0 | 0 | 5858494.36 | 5858494.36 | 0 | 5858494.36 | 100% | 0
1470900 | 11050 | Other Land Costs | 200754.83 | -49410.84 | 0 | 151343.99 | 151343.99 | 0 | 151343.99 | 100% | 0
|  | Total Land Cost | 6059249.19 | -49410.84 | 0 | 6009838.35 | 6009838.35 | 0 | 6009838.35 | 100% | 0
| 11110 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11120 | Offsite Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11130 | Site Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1102605 | 11140 | Utilities Relocation | 150000 | 62251 | 0 | 212251 | 62251.02 | 0 | 62251.02 | 29.33% | 149999.98
|  | Total Site Work | 150000 | 62251 | 0 | 212251 | 62251.02 | 0 | 62251.02 | 29.33% | 149999.98
1279100 | 11230 | Other Construction Costs | 400000 | -310000 | 0 | 90000 | 0 | 0 | 0 | 0% | 90000
| 11220 | Garage Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1101002 | 11210 | Base Construction Costs | 38698021.05 | 9300271.95 | 0 | 47998293 | 0 | 0 | 0 | 0% | 47998293
| 11250 | Retail Construction Costs/White Box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11240 | Inflation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11310 | Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11320 | Landlord Tenant Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11330 | Commercial Tenant Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11340 | GMAX Contract Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11350 | Options and Selections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11410 | Clubhouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11420 | Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11430 | Other Structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11440 | Other Amenities (Owner Wish List) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11450 | Amenities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1279100 | 11610 | Model Furnishings | 40000 | -40000 | 0 | 0 | 0 | 0 | 0 | 0% | 0
1279100 | 11620 | Common Area Furnishings | 250000 | 661505.77 | 0 | 911505.77 | 0 | 0 | 0 | 0% | 911505.77
| 11630 | Audio, Visual, and Security Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11631 | Televisions and Appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1279100 | 11640 | Fitness and Bicycle Equipment | 105000 | -39000 | 0 | 66000 | 0 | 0 | 0 | 0% | 66000
1279100 | 11650 | Outdoor Furniture and Equipment | 125000 | -125000 | 0 | 0 | 0 | 0 | 0 | 0% | 0
1279100 | 11660 | Office Furniture and Equipment | 110000 | -59809 | 0 | 50191 | 0 | 0 | 0 | 0% | 50191
1279100 | 11670 | Maintenance Equipment | 42500 | -1300 | 0 | 41200 | 0 | 0 | 0 | 0% | 41200
| 11680 | Security Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11690 | Other FF&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1144012 | 13010 | Hard Cost Contingency (Excludes Land) | 1914611.1 | 489803.9 | 0 | 2404415 | 0 | 0 | 0 | 0% | 2404415
1284100 | 13020 | Soft Cost Contingency | 282434.29 | -20494.29 | -13681.74 | 248258.26 | 0 | 0 | 0 | 0% | 248258.26
1284104 |  | Working Capital | 0 | 150000 | 0 | 150000 | 150000 | 0 | 150000 | 100% | 0
|  | Construction Costs | 41967566.44 | 10005978.33 | -13681.74 | 51959863.03 | 150000 | 0 | 150000 | 0.2887% | 51809863.03
| 11810 | Sanitary Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11815 | Water Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1276100 | 11820 | Building Permits | 150000 | 0 | 0 | 150000 | 98975.15 | 17187.22 | 116162.37 | 77.44% | 33837.63
#N/A | 11830 | CO Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11840 | A&E Permit Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11850 | File & Review Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11860 | Tax Abatement | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11870 | Zoning Variances Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11880 | Impact Fees - General | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11881 | Impact Fees - Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11882 | Impact Fees - Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11883 | Impact Fees - Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11884 | Impact Fees - Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11885 | Impact Fees - School | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11886 | Impact Fees - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Permits and Fees | 150000 | 0 | 0 | 150000 | 98975.15 | 17187.22 | 116162.37 | 77.44% | 33837.63
| 11510 | Owner's Representative | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11511 | Construction Coordinator | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11512 | Construction Trailer | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11513 | Construction Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11514 | Other Salaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11520 | Estimating Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11530 | Office Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11540 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 11505 | Precon Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1273509 | 11506 | Construction Management | 540000 | 94000 | 0 | 634000 | 126000 | 14000 | 140000 | 22.08% | 494000
#N/A | 11710 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11711 | Title | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11712 | Geo-technical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11713 | Environmental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11720 | Market Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11721 | Traffic Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1273508 | 11730 | Inspections | 110000 | 0 | 0 | 110000 | 0 | 0 | 0 | 0% | 110000
| 11740 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11750 | Meals & Entertainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1273156 | 11760 | Other Due Diligence | 168137.73 | 126797.27 | 0 | 294935 | 68943.64 | -5084 | 63859.64 | 21.65% | 231075.36
#N/A | 11910 | Easement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11911 | Purchase Agreement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11912 | Zoning & Appro. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11913 | Applications & Permits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11914 | Corporate Set Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11915 | Litigation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11920 | Professional Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11930 | HPR Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11940 | Tenant Leasing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11945 | Public Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11946 | TIF Financing-City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11947 | TIF Financing-Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11950 | Debt Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11951 | Investor Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11952 | Private Placement Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11953 | Closing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11955 | Acquisitions & Dispositions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 11960 | Sales & Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1280100 | 11970 | Other Legal | 150000 | 115000 | 4999 | 269999 | 109277.13 | 123102.34 | 232379.47 | 86.07% | 37619.53
#N/A | 12010 | Construction Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12011 | Platting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12012 | Conceptual Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1272200 | 12013 | Civil Engineering Plans | 287506.73 | 174746.27 | 13681.74 | 475934.74 | 461588.86 | 14345.88 | 475934.74 | 100% | 0
#N/A | 12014 | Condominium Docs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12015 | Feasibility/Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12018 | Landscape Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12020 | Reimbursables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12030 | As-Built Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12031 | Tree Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12040 | Revisions/Change Orders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12050 | Quality/Materials Testing/ADA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12060 | Condo Document Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12070 | Engineering % of Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12110 | Construction Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12111 | Platting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12112 | Conceptual Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12113 | Schematic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12114 | Design Development Refinement Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1271100 | 12115 | Construction Documents Phase | 1087650 | -92000 | 0 | 995650 | 809848.5 | 0 | 809848.5 | 81.34% | 185801.5
#N/A | 12116 | Interior Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12117 | Landscape Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12120 | Structural Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12121 | Code Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12122 | HVAC Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12123 | Electrical Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12124 | Plumbing Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12125 | LEED Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12126 | LEED Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1273100 | 12127 | General Consultant | 150000 | 441200 | 0 | 591200 | 27225 | 0 | 27225 | 4.605% | 563975
#N/A | 12128 | Accessibility Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12129 | Pool Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12131 | Moisture Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12140 | Renderings & Models | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12141 | Reproduction/Printing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1277530 | 12142 | Reimbursable | 25000 | 0 | 0 | 25000 | 3137.19 | 123.59 | 3260.78 | 13.04% | 21739.22
#N/A | 12150 | Revisions/Change Orders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12160 | Bidding, Negotiation & Admin Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12170 | Travel - Architectural and Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12180 | Permits/Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| 12190 | Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12195 | Architectural % of Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12210 | Corp Setup accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12220 | Tax Preparation accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1277525 | 12230 | Professional Services accounting | 160100 | 31339 | 0 | 191439 | 71888.5 | 4725 | 76613.5 | 40.02% | 114825.5
1273155 | 12231 | Other Accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Total Design and Engineering Consultants | 2678394.46 | 891082.54 | 18680.74 | 3588157.74 | 1677908.82 | 151212.81 | 1829121.63 | 50.98% | 1759036.11
| 12310 | Appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12311 | Market/Feasibility Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12320 | Predevelopment Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12322 | Investor Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12330 | Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12331 | Points on Equity (LP Fee) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1286002 | 12332 | Debt Placement Fee | 565259.37 | -75259.3695 | 0 | 490000.0005 | 490000 | 0 | 490000 | 100% | 0.00048195
| 12333 | Development Oversight Fee (LP FEE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1281125 | 12340 | Closing Fees | 188419.79 | -28100.74 | -4999 | 155320.05 | 259810.8 | -104490.75 | 155320.05 | 100% | 0
| 12350 | Bank Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12360 | Inspections/Feasibility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12361 | Architectural Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
#N/A | 12362 | Title Updates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12370 | Letter of Credit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12380 | Applications Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12385 | Other Finance Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1282100 | 12410 | Property Tax | 1102519.52 | 253862.48 | 0 | 1356382 | 159159.25 | 0 | 159159.25 | 11.73% | 1197222.75
1281143 | 12334 | Guarantee Fee | 0 | 400000.0013 | 0 | 400000.0013 | 0 | 0 | 0 | 0% | 400000.0013
1279200 | 12390 | LeaseUp Operating Deficits | 379456.78 | -95079.95 | 0 | 284376.83 | 0 | 0 | 0 | 0% | 284376.83
1281121 | 12321 | Construction Period Interest | 1241258.41 | -259417.41 | 0 | 981841 | 0 | 0 | 0 | 0% | 981841
|  | Total Financing & Other Costs | 3476913.87 | 196005.0118 | -4999 | 3667919.8818 | 908970.05 | -104490.75 | 804479.3 | 21.93% | 2863440.5818
| 12710 | Copies & Reproduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12711 | Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1277531 | 12720 | Travel | 10000 | 22000 | 0 | 32000 | 5108.48 | 239.09 | 5347.57 | 16.71% | 26652.43
#N/A | 12730 | Meals & Entertainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12740 | Janitorial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1277900 | 12741 | Maintenance | 42500 | -34500 | 0 | 8000 | 1000 | 0 | 1000 | 12.5% | 7000
#N/A | 12750 | Association Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12760 | Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12770 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1275001 | 12420 | Builder's Risk Insurance | 329571.81 | 414814.19 | 0 | 744386 | 0 | 0 | 0 | 0% | 744386
1275001 | 12421 | Property Insurance | 25000 | -24500 | 0 | 500 | 256 | 0 | 256 | 51.2% | 244
1275001 | 12422 | OCIP | 365000 | 93520 | 0 | 458520 | 0 | 437249.76 | 437249.76 | 95.36% | 21270.24
| 12423 | Telecommunications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12424 | Electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
| 12425 | Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12426 | Water/Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12810 | Warranty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12830 | Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
| 12840 | Other Warranty and Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
1278200 | 12910 | Developer Fee | 1485567.04 | -108132.04 | 0 | 1377435 | 0 | 0 | 0 | 0% | 1377435
#REF! | 12912 | Development Fee - BROZ 5321 Fund LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Total Other Development Costs | 2257638.85 | 363202.15 | 0 | 2620841 | 6364.48 | 437488.85 | 443853.33 | 16.94% | 2176987.67
| 12502 | Marketing Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12504 | Digital and Web | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12506 | Renderings | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12508 | Virtual Tours | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12512 | Brochures | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12514 | Floor plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12516 | Flyers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12518 | Outreach Gifts | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12519 | Move-in Gifts | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12521 | Letterhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12522 | Note Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12525 | Envelopes | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12526 | Business Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12528 | Outreach Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12531 | Signage-Temporary | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12532 | Monument | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12534 | Internal Displays | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12536 | Call Outs | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12538 | Offsite | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12542 | Press Releases | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12544 | Photography | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12545 | Direct Mailers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12546 | Placements | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12548 | Sponsorships | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12552 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12554 | Furniture Rental | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12555 | Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12556 | Restroom Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12558 | Telephone/Internet | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12562 | Sales Displays | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12564 | Office Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12565 | Memberships/Subscriptions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12566 | Education/Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12568 | Food & Beverage | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12572 | Events | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12574 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12576 | Bonuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12578 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12592 | Internal Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12594 | Broker Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12596 | Closing Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
1277410 | 12597 | Other Marketing | 123200 | 123200 | 0 | 246400 | 4500 | 0 | 4500 | 1.826% | 241900
| 12610 | Advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12620 | Marketing Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12760 | Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12640 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12670 | Commercial Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 12680 | Other Commercial Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Total Leasing and Marketing | 123200 | 123200 | 0 | 246400 | 4500 | 0 | 4500 | 1.826% | 241900
|  | Zone Project Costs - All | 56862962.81 | 11592308.1918 | 0 | 68455271.0018 | 8918807.87 | 501398.13 | 9420206 | 13.76% | 59035065.0018
|  |  |  | Total project costs incurred per GL |  |  |  |  | 8832956.24
|  |  |  | Total project costs incurred per Master report |  |  |  |  | 9420206
|  |  |  | Discrepancy |  |  |  |  | -587249.76
Project costs recorded in GL but not in Master report
|  |  |  | Development fee |  |  |  |  | 0
0
-587249.76
Sources
|  | JPM Bank Loan | 31274629.55 | 8725370.45 | 0 | 40000000 | 0 | 0 | 0 | 0% | 40000000
|  | Bridge Equity | 24308916.6 | 2723590.8518 | 0 | 27032507.4518 | 8472669.27 | 476526.428 | 8949195.698 | 33.11% | 18083311.7538
|  | BROZ Dallas Fund Equity | 1279416.66 | 143346.89 | 0 | 1422763.55 | 445929.96 | 25080.342 | 471010.302 | 33.11% | 951753.248
|  | Total Sources | 56862962.81 | 11592308.1918 | 0 | 68455271.0018 | 8918599.23 | 501606.77 | 9420206 | 13.76% | 59035065.0018
[7 empty] | 208.64 | -208.64 | 0

## Budget to Actual (2) (hidden)
PROJECT FUNDING REQUISITION
#REF!
46203
0
|  | Bishop Arts | Previous Contingency | Current Contingency | Bishop Arts | Previous Application | Payment this period | Total Complete & Draw To Date |  | Balance remaining
COA# | Account Name | Approved JVA Budget | Funding & Reallocation | Funding & Reallocation | Current Approved Budget | Inception to 6/30/2022 | 7/31/2022 | Incurred to 7/31/2022 | Percent Drawn | As of 7/31/2022
11010 | Land Purchase | 5858494.36 | 0 | 0 | 5858494.36 | 5858494.36 | 0 | 5858494.36 | 100% | 0
11050 | Other Land Costs | 200754.83 | -49410.84 | 0 | 151343.99 | 151343.99 | 0 | 151343.99 | 100% | 0
| Total Land Cost | 6059249.19 | -49410.84 | 0 | 6009838.35 | 6009838.35 | 0 | 6009838.35 | 100% | 0
11110 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11120 | Offsite Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11130 | Site Work | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11140 | Utilities Relocation | 150000 | 62251 | 0 | 212251 | 62251.02 | 0 | 62251.02 | 29.33% | 149999.98
| Total Site Work | 150000 | 62251 | 0 | 212251 | 62251.02 | 0 | 62251.02 | 29.33% | 149999.98
11230 | Other Construction Costs | 400000 | -310000 | 0 | 90000 | 0 | 0 | 0 | 0% | 90000
11220 | Garage Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11210 | Base Construction Costs | 38698021.05 | 9454867.37 | 0 | 48152888.42 | 6814171.26 | 505411.87 | 7319583.13 | 15.2% | 40833305.29
11250 | Retail Construction Costs/White Box | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11240 | Inflation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11310 | Upgrades | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11320 | Landlord Tenant Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11330 | Commercial Tenant Improvements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11340 | GMAX Contract Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11350 | Options and Selections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11410 | Clubhouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11420 | Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11430 | Other Structures | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11440 | Other Amenities (Owner Wish List) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11450 | Amenities | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11610 | Model Furnishings | 40000 | -40000 | 0 | 0 | 0 | 0 | 0 | 0% | 0
11620 | Common Area Furnishings | 250000 | 661505.77 | 0 | 911505.77 | 0 | 0 | 0 | 0% | 911505.77
11630 | Audio, Visual, and Security Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11631 | Televisions and Appliances | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11640 | Fitness and Bicycle Equipment | 105000 | -39000 | 0 | 66000 | 32330.93 | 0 | 32330.93 | 48.99% | 33669.07
11650 | Outdoor Furniture and Equipment | 125000 | -125000 | 0 | 0 | 0 | 0 | 0 | 0% | 0
11660 | Office Furniture and Equipment | 110000 | -59809 | 0 | 50191 | 0 | 0 | 0 | 0% | 50191
11670 | Maintenance Equipment | 42500 | -1300 | 0 | 41200 | 0 | 0 | 0 | 0% | 41200
11680 | Security Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11690 | Other FF&E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
13010 | Hard Cost Contingency (Excludes Land) | 1914611.1 | 335208.48 | 0 | 2249819.58 | 0 | 0 | 0 | 0% | 2249819.58
13020 | Soft Cost Contingency | 282434.29 | -121013.02 | -2438.18 | 158983.09 | 0 | 0 | 0 | 0% | 158983.09
| Working Capital | 0 | 150000 | 0 | 150000 | 150000 | 0 | 150000 | 100% | 0
| Construction Costs | 41967566.44 | 9905459.6 | -2438.18 | 51870587.86 | 6996502.19 | 505411.87 | 7501914.06 | 14.46% | 44368673.8
11810 | Sanitary Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11815 | Water Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11820 | Building Permits | 150000 | 0 | 0 | 150000 | 134442.37 | 0 | 134442.37 | 89.63% | 15557.63
11830 | CO Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11840 | A&E Permit Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11850 | File & Review Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11860 | Tax Abatement | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11870 | Zoning Variances Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11880 | Impact Fees - General | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11881 | Impact Fees - Water | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11882 | Impact Fees - Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11883 | Impact Fees - Park | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11884 | Impact Fees - Road | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11885 | Impact Fees - School | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11886 | Impact Fees - Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Permits and Fees | 150000 | 0 | 0 | 150000 | 134442.37 | 0 | 134442.37 | 89.63% | 15557.63
11510 | Owner's Representative | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11511 | Construction Coordinator | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11512 | Construction Trailer | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11513 | Construction Manager | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11514 | Other Salaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11520 | Estimating Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11530 | Office Expenses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11540 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11505 | Precon Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
11506 | Construction Management | 540000 | 94000 | 0 | 634000 | 260000 | 20000 | 280000 | 44.16% | 354000
11710 | Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11711 | Title | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11712 | Geo-technical | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11713 | Environmental | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11720 | Market Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11721 | Traffic Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11730 | Inspections | 110000 | 0 | 0 | 110000 | 29050 | 0 | 29050 | 26.41% | 80950
11740 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11750 | Meals & Entertainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11760 | Other Due Diligence | 168137.73 | 126797.27 | 0 | 294935 | 117436.63 | 4620.63 | 122057.26 | 41.38% | 172877.74
11910 | Easement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11911 | Purchase Agreement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11912 | Zoning & Appro. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11913 | Applications & Permits | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11914 | Corporate Set Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11915 | Litigation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11920 | Professional Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11930 | HPR Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11940 | Tenant Leasing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11945 | Public Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11946 | TIF Financing-City | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11947 | TIF Financing-Owner | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11950 | Debt Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11951 | Investor Financing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11952 | Private Placement Documents | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11953 | Closing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11955 | Acquisitions & Dispositions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11960 | Sales & Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
11970 | Other Legal | 150000 | 119999 | 0 | 269999 | 245310.03 | 3463.5 | 248773.53 | 92.14% | 21225.47
12010 | Construction Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12011 | Platting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12012 | Conceptual Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12013 | Civil Engineering Plans | 287506.73 | 257537.76 | 2438.18 | 547482.67 | 545044.49 | 2438.18 | 547482.67 | 100% | 0
12014 | Condominium Docs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12015 | Feasibility/Testing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12018 | Landscape Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12020 | Reimbursables | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12030 | As-Built Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12031 | Tree Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12040 | Revisions/Change Orders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12050 | Quality/Materials Testing/ADA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12060 | Condo Document Survey | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12070 | Engineering % of Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12110 | Construction Coordination | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12111 | Platting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12112 | Conceptual Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12113 | Schematic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12114 | Design Development Refinement Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12115 | Construction Documents Phase | 1087650 | -92000 | 0 | 995650 | 838208.5 | 5775 | 843983.5 | 84.77% | 151666.5
12116 | Interior Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12117 | Landscape Architect | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12120 | Structural Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12121 | Code Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12122 | HVAC Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12123 | Electrical Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12124 | Plumbing Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12125 | LEED Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12126 | LEED Commissioning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12127 | General Consultant | 150000 | 441200 | 0 | 591200 | 30975 | 0 | 30975 | 5.239% | 560225
12128 | Accessibility Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12129 | Pool Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12131 | Moisture Consultant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12140 | Renderings & Models | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12141 | Reproduction/Printing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12142 | Reimbursable | 25000 | 0 | 0 | 25000 | 3356.22 | 0 | 3356.22 | 13.42% | 21643.78
12150 | Revisions/Change Orders | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12160 | Bidding, Negotiation & Admin Phase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12170 | Travel - Architectural and Design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12180 | Permits/Approval | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
12190 | Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12195 | Architectural % of Construction Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12210 | Corp Setup accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12220 | Tax Preparation accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12230 | Professional Services accounting | 160100 | 31339 | 0 | 191439 | 118838.5 | 4725 | 123563.5 | 64.54% | 67875.5
12231 | Other Accounting | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Design and Engineering Consultants | 2678394.46 | 978873.03 | 2438.18 | 3659705.67 | 2188219.37 | 41022.31 | 2229241.68 | 60.91% | 1430463.99
12310 | Appraisal | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12311 | Market/Feasibility Study | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12320 | Predevelopment Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12322 | Investor Interest | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12330 | Points | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12331 | Points on Equity (LP Fee) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12332 | Debt Placement Fee | 565259.37 | -75259.3695 | 0 | 490000.0005 | 490000 | 0 | 490000 | 100% | 0.00048195
12333 | Development Oversight Fee (LP FEE) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12340 | Closing Fees | 188419.79 | -33099.74 | 0 | 155320.05 | 155320.05 | 0 | 155320.05 | 100% | 0
12350 | Bank Charges | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12360 | Inspections/Feasibility | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12361 | Architectural Inspections | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12362 | Title Updates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12370 | Letter of Credit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12380 | Applications Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12385 | Other Finance Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12410 | Property Tax | 1102519.52 | 253862.48 | 0 | 1356382 | 159159.25 | 0 | 159159.25 | 11.73% | 1197222.75
12334 | Guarantee Fee | 0 | 400000.0013 | 0 | 400000.0013 | 0 | 0 | 0 | 0% | 400000.0013
12390 | LeaseUp Operating Deficits | 379456.78 | -95079.95 | 0 | 284376.83 | 0 | 0 | 0 | 0% | 284376.83
12321 | Construction Period Interest | 1241258.41 | -259417.41 | 0 | 981841 | 0 | 0 | 0 | 0% | 981841
| Total Financing & Other Costs | 3476913.87 | 191006.0118 | 0 | 3667919.8818 | 804479.3 | 0 | 804479.3 | 21.93% | 2863440.5818
12710 | Copies & Reproduction | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12711 | Postage & Delivery | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12720 | Travel | 10000 | 22000 | 0 | 32000 | 24093.93 | 1364.18 | 25458.11 | 79.56% | 6541.89
12730 | Meals & Entertainment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12740 | Janitorial | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12741 | Maintenance | 42500 | -34500 | 0 | 8000 | 1000 | 0 | 1000 | 12.5% | 7000
12750 | Association Fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12760 | Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12770 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12420 | Builder's Risk Insurance | 329571.81 | 414814.19 | 0 | 744386 | 547819.47 | 0 | 547819.47 | 73.59% | 196566.53
12421 | Property Insurance | 25000 | -24500 | 0 | 500 | 256 | 0 | 256 | 51.2% | 244
12422 | OCIP | 365000 | 111247.24 | 0 | 476247.24 | 476247.24 | 0 | 476247.24 | 100% | 0
12423 | Telecommunications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12424 | Electricity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0
12425 | Gas | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12426 | Water/Sewer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12810 | Warranty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12830 | Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12840 | Other Warranty and Reserves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0! | 0
12914 | Developer Fee | 1485567.04 | -108132.04 | 0 | 1377435 | 265062.89 | 13153.13 | 278216.02 | 20.2% | 1099218.98
12912 | Development Fee - BROZ 5321 Fund LLC | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Other Development Costs | 2257638.85 | 380929.39 | 0 | 2638568.24 | 1314479.53 | 14517.31 | 1328996.84 | 50.37% | 1309571.4
12502 | Marketing Firm | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12504 | Digital and Web | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12506 | Renderings | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12508 | Virtual Tours | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12512 | Brochures | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12514 | Floor plans | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12516 | Flyers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12518 | Outreach Gifts | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12519 | Move-in Gifts | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12521 | Letterhead | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12522 | Note Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12525 | Envelopes | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12526 | Business Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12528 | Outreach Cards | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12531 | Signage-Temporary | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12532 | Monument | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12534 | Internal Displays | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12536 | Call Outs | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12538 | Offsite | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12542 | Press Releases | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12544 | Photography | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12545 | Direct Mailers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12546 | Placements | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12548 | Sponsorships | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12552 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12554 | Furniture Rental | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12555 | Utilities | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12556 | Restroom Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12558 | Telephone/Internet | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12562 | Sales Displays | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12564 | Office Supplies | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12565 | Memberships/Subscriptions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12566 | Education/Training | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12568 | Food & Beverage | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12572 | Events | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12574 | Travel | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12576 | Bonuses | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12578 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12592 | Internal Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12594 | Broker Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12596 | Closing Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12597 | Other Marketing | 123200 | 123200 | 0 | 246400 | 4500 | 0 | 4500 | 1.826% | 241900
12610 | Advertising | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12620 | Marketing Material | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12760 | Signage | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12640 | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12670 | Commercial Commissions | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
12680 | Other Commercial Marketing | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Total Leasing and Marketing | 123200 | 123200 | 0 | 246400 | 4500 | 0 | 4500 | 1.826% | 241900
| Zone Project Costs - All | 56862962.81 | 11592308.1918 | 0 | 68455271.0018 | 17514712.13 | 560951.49 | 18075663.62 | 26.41% | 50379607.3818
Total project costs incurred per GL
Total project costs incurred per Master report
Discrepancy
Project costs recorded in GL but not in Master report
Development fee